## Contents
GINR Activity: Dec 01, 2018 to Dec 31, 2018
Table of Contents
Disclaimer and References | Disclaimer on the use of this report, and references to associated ERCOT Binding Documents ***Please read***
Acronyms | A list of the various acronyms used throughout the report
Summary | Tables that provide project aggregate counts and megawatt capacities by GINR phase and fuel type
Project Commissioning Update | A table listing project commissioning approval milestones met for the month: energization, synchronization, and commercial operations approval
Project Cancellation Update | A table listing the projects cancelled for the month
Project Details | A table that lists project details; only includes projects for which a Full Interconnection Study has been requested
GINR Trends | Charts and tables that show historical and projected interconnection study trends.
Time of Report Run: Jan 1, 2019 9:16:00 AM

## Disclaimer and References
Generator Interconnection Status Report - Disclaimer
FOR PLANNING PURPOSES ONLY
This ERCOT Working Paper has been prepared for specific ERCOT and Market Participant purposes, and has been
developed from data provided by Interconnecting Entities and Transmission Service Providers that has been entered into the online GINR system.
The data may contain errors or be obsolete depending on when the data was entered. ERCOT MAKES NO WARRANTY, EXPRESS
OR IMPLIED,INCLUDING ANY WARRANTY OF MERCHANTABILITY OR FITNESS FOR ANY PARTICULAR PURPOSE,
AND DISCLAIMS ANY AND ALL LIABILITY WITH RESPECT TO THE ACCURACY OF SAME OR THE FITNESS OR
APPROPRIATENESS OF SAME FOR ANY PARTICULAR USE. THIS ERCOT WORKING PAPER IS SUPPLIED WITH ALL FAULTS.
References
The links below provide more information on the ERCOT interconnection process:
http://www.ercot.com/mktrules/guides/planning/current
http://www.ercot.com/services/rq/re/reg/Resource%20Interconnection%20Handbook.pdf

## Acronyms
Acronyms
GINR = Generation Interconnection or Change Request
COD: Commercial Operation Date
SS = Security Screening Study
FIS = Full Interconnection Study
IA = Interconnection Agreement; can be either of the following:
- Standard Generation Interconnection Agreement (SGIA)
- Public financially binding agreement
- An official letter from a Municipally Owned Utility or Electric Cooperative signifying developer intent to build and operate generation facilities and interconnect with the MOU or EC
POI = Point of lnterconnection
INR = Interconnection Request Number
TSP = Transmission Service Provider
NtP = Notice-to-Proceed given to the TSP for interconnection construction
CDR: Capacity, Demand and Reserves Report
SFS: Sufficient Financial Security provided to the TSP for construction of the interconnection facilities
QSA: Quarterly Stability Assessment
Fuel Types | Technology Types
BIO = Biomass | BA = Battery Energy Storage
COA = Coal | CC = Combined-Cycle
GAS = Gas | CE = Compressed Air Energy Storage
GEO = Geothermal | CP = Concentrated Solar Power
HYD = Hydrogen | EN = Energy Storage
NUC = Nuclear | FC = Fuel Cell
OIL = Fuel Oil | GT = Combustion (gas) Turbine, but not part of a Combined-Cycle
OTH = Other | HY = Hydroelectric Turbine
PET = Petcoke | IC = Internal Combustion Engine, eg. Reciprocating
SOL = Solar | OT = Other
WAT = Water | PV = Photovoltaic Solar
WIN = Wind | ST = Steam Turbine other than Combined-Cyclw
WT = Wind Turbine

## Summary
Summary |  |  | Major GINR Milestone Status by Fuel/Technology Type, MW
Currently tracking 465 generation interconnection or change requests as of Dec 31, 2018 |  |  | Includes only those projects for which a Security Screening Study (SS) has been requested.
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  |  | Fuel | Technology | SS Started | SS Started | SS Completed | SS Completed | SS Completed | SS Completed | SS Completed | TOTAL
Includes only those projects for which a Security Screening Study (SS) is underway |  |  | Type | Type | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | FIS Started | FIS Completed
[5 empty] | No IA | No IA | No IA | No IA | No IA | IA | IA
Status of SS, FIS, and IA | Project Count | % of Total | Gas | Combined-Cycle |  |  |  | 1502.5 |  | 1485.8 | 12 | 3000.3
SS Started, FIS Not Started, No IA | 31 | 6.667% | Gas | Combustion Turbine | 450 | 968 | 1350 | 1763.3 | 100 | 881.8 | 318 | 5831.1
SS Started, FIS Started, No IA | 8 | 1.72% | Gas | Internal Combustion Engine
SS Completed, FIS Not Started, No IA | 67 | 14.41% | Gas | Compressed Air Energy Storage | 328 | [6 empty] | 328
SS Completed, FIS Started, No IA | 229 | 49.25% | Gas | Steam Turbine |  |  | 90 |  |  |  |  | 90
SS Completed, FIS Completed, No IA | 27 | 5.806% | Gas | Total gas | 778 | 968 | 1440 | 3265.8 | 100 | 2367.6 | 330 | 9249.4
SS Completed, FIS Started, IA | 48 | 10.32% | Coal
SS Completed, FIS Completed, IA | 55 | 11.83% | Wind |  | 346.4 |  | 6232.8 | 18217.2 | 519 | 6451.51 | 7829.54 | 39596.45
Total Interconnection Requests | 465 |  | Solar |  | 6233.1 | 947.43 | 5710.73 | 22897.27 | 606.9 | 3419.66 | 917.4 | 40732.49
Cancelled Studies (since last month) | 9 |  | Biomass
| Capacity, MW |  | Other | Battery | 116 | 242.22 | 430.5 | 1554.1 |  |  |  | 2342.82
Total Capacity Under Study | 91921.16 |  | Other*
Interconnection Agreements Executed | 21315.71 |  | TOTAL |  | 7473.5 | 2157.65 | 13814.03 | 45934.37 | 1225.9 | 12238.77 | 9076.94 | 91921.16
Cancelled (since last month) | 1981 |  | * Other includes petroleum coke (pet coke), hydroelectric, fuel oil, geothermal energy, and other miscellaneous fuels reported by developers.

## Project Commissioning Update
Commissioning Approvals During December 2018
Commissioning Category | INR | Project Name | Fuel | County | Approval Date * | MW **
Commercial Operation Approved by ERCOT* | 15INR0035 | Stella 1 Wind | Wind | Kenedy | 2018-12-19 | 201
Commercial Operation Approved by ERCOT* | 16INR0023b | Lamesa Solar B (Phase II) IVORY | Solar | Dawson | 2018-12-19 | 50
Commercial Operation Approved by ERCOT* | 16INR0115 | Waymark Solar | Solar | Pecos | 2018-12-20 | 182
Synchronization Approved by ERCOT | 11INR0054 | Midway Wind | Wind | San Patricio | 2018-12-04 | 162.9
Synchronization Approved by ERCOT | 18INR0078 | Bobcat Bluff repower | Wind | Archer | 2018-12-20 | 12
Synchronization Approved by ERCOT | 18INR0079 | Woodward I repower | Wind | Pecos | 2018-12-18 | 0
Synchronization Approved by ERCOT | 18INR0080 | Woodward 2 repower | Wind | Pecos | 2018-12-19 | 0
Synchronization Approval Revoked by ERCOT | 17INR0022 | MIRAGE | Gas | Harris | 2018-12-19 | 11
Energization Approved by ERCOT | 18INR0070 | Blue Summit II | Wind | Wilbarger | 2018-12-18 | 102
* For projects approved for commercial operations, the approval date is the Resource Commissioning Date defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a
Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative
values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.

## Project Cancellation Update
Projects Cancelled by the Developer during December 2018*
INR | Project Name | Fuel | County | Cancel Date | MW **
18INR0022 | Winkler Solar | Solar | Winkler | 2018-12-07 10:32 | 150
18INR0057 | Green Valley Wind | Wind | Val Verde | 2018-12-20 15:42 | 500
19INR0139 | Craver Ranch | Solar | Denton | 2018-12-20 09:51 | 100
* Includes only those projects cancelled after the developer makes a Full Interconnection Study (FIS) request.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.

## Project Details
GINR Project Details
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study has been requested are included.
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GINR system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not obtained or reported to ERCOT yet.
Project Attributes | [10 empty] | Changes from Last Report | GINR Project Milestone Dates
INR | Project Name | GINR Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | IA Signed | Financial Security | Air Permit | GHG Permit | Water Availability | Meets Planning Guide Section 6.9(1) | Meets Planning Guide Section 6.9 | Meets Planning Guide | Construction Start | Construction End | Approved for Energization | Approved for Synchronization
[11 empty] | Change indicators: Proj Name, MW | [5 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[11 empty] | Size , COD, SFS/NtP, FIS Request | [5 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[21 empty] | Models | Models
08INR0019b | Grandview 5 W | SS Completed, FIS Started, No IA | Eon | 79005 Railhead 345kV | Gray | PANHANDLE | 2020-12-15 | WIN | WT | 249 |  | 2006-07-21 | 2006-10-02 | 2006-07-21 |  |  | No | Not Required | Not Required | Not Required
11INR0054 | Midway Wind | SS Completed, FIS Completed, IA | Apex Clean | 8961 Whitepoint 138kV | San Patricio | COASTAL | 2018-12-15 | WIN | WT | 162.9 |  | 2009-02-26 | 2009-05-28 | 2009-11-30 | 2018-04-19 | 2017-11-05 | Yes | Not Required | Not Required | Not Required | 2018-04-24 | 2018-09-28 | 2018-04-24 |  |  | 2018-10-23 | 2018-12-04
11INR0062 | Shaffer | SS Completed, FIS Completed, IA | NRG | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2019-03-08 | WIN | WT | 226 | COD | 2009-04-23 | 2009-06-16 | 2009-07-21 | 2018-06-13 | 2018-04-13 | Yes | Not Required | Not Required | Not Required | 2018-04-18 | 2018-09-28 | 2018-04-18
12INR0002a | Silver Canyon Wind A | SS Completed, FIS Completed, IA | EDP Renewables | 79503 Tule Canyon 345kV | Briscoe | PANHANDLE | 2020-10-31 | WIN | WT | 200 |  | 2007-01-03 | 2007-01-26 | 2007-07-31 | 2018-08-30 | 2016-06-22 | No | Not Required | Not Required | Not Required
12INR0029 | Comanche Run Wind | SS Completed, FIS Started, IA | Avangrid | 79501 Ogallala 345kV | Swisher | PANHANDLE | 2019-12-31 | WIN | WT | 500 |  | 2009-03-02 | 2009-05-28 | 2009-07-01 |  | 2013-07-24 | No | Not Required | Not Required | Not Required
12INR0055 | S_Hills Wind | SS Completed, FIS Completed, IA | SEYMOUR HILLS WIND PROJECT, LLC | 33728 Mabelle 69kV | Baylor | WEST | 2019-04-01 | WIN | WT | 30.24 |  | 2010-09-28 | 2010-12-20 | 2016-08-17 | 2018-06-19 | 2017-12-04 | Yes | Not Required | Not Required | Not Required | 2018-10-04 |  | 2018-10-04
12INR0059b | HOVEY (Barilla Solar 1B) | SS Completed, FIS Completed, IA | First Solar | 60385 Solstice 138kV | Pecos | WEST | 2019-02-28 | SOL | PV | 7.4 |  | 2010-12-01 | 2011-02-25 | 2011-08-09 | 2014-01-16 | 2013-12-26 | Yes | Not Required | Not Required | Not Required
12INR0060 | Wilson Ranch | SS Completed, FIS Completed, IA | ENGIE | 76003 Big Hill 345kV | Schleicher | WEST | 2019-01-24 | WIN | WT | 199.5 |  | 2010-12-03 | 2014-03-21 | 2011-06-06 | 2018-05-31 | 2018-05-21 | Yes | Not Required | Not Required | Not Required | 2018-05-21 | 2018-09-28 | 2018-05-21 |  |  | 2018-10-11 | 2018-11-29
13INR0010a | Mariah Del Este | SS Completed, FIS Started, IA | Mariah Acquisition | 141765 Mariah 345kV | Parmer | PANHANDLE | 2019-03-29 | WIN | WT | 152.5 | COD | 2009-06-29 | 2009-09-25 | 2010-03-26 |  | 2013-01-31 | Yes | Not Required | Not Required | Not Required | 2018-04-30 | 2018-04-30 | 2018-04-30
13INR0010def | Scandia Wind DEF | SS Completed, FIS Completed, IA | Scandia Wind LLC | 141765 Mariah 345kV | Parmer | PANHANDLE | 2020-04-01 | WIN | WT | 600.3 |  | 2009-06-29 | 2009-09-25 | 2010-03-26 | 2017-08-03 | 2014-04-25 | No | Not Required | Not Required | Not Required
13INR0025 | Northdraw Wind | SS Completed, FIS Started, IA | National Renewable Solutions | 79504 AJ Swope 345kV | Randall | PANHANDLE | 2020-08-01 | WIN | WT | 150 | COD | 2010-06-15 | 2010-09-02 | 2011-03-01 |  | 2018-04-25 | No | Not Required | Not Required | Not Required
13INR0026 | Canadian Breaks Wind | SS Completed, FIS Completed, IA | Macquarie Cap | Tap 345kV 79502 Windmill - 79504 AJ Swope | Oldham | PANHANDLE | 2019-09-13 | WIN | WT | 210 |  | 2010-07-06 | 2010-10-04 | 2011-04-01 | 2017-03-16 | 2016-05-20 | Yes | Not Required | Not Required | Not Required | 2018-09-04 | 2018-10-30 | 2018-09-04
13INR0038 | Wildrose Wind | SS Completed, FIS Started, IA | S Power | 79501 Ogallala 345kV | Swisher | PANHANDLE | 2020-12-30 | WIN | WT | 302.5 |  | 2011-05-01 | 2011-05-26 | 2011-11-02 |  | 2015-09-06 | Yes | Not Required | Not Required | Not Required | 2017-05-04 |  | 2017-05-04
14INR0009 | WKN Amadeus Wind | SS Completed, FIS Started, IA | WKN | tap 345kV 11305 Dermott - 60704 Kirchhof | Fisher | WEST | 2020-05-15 | WIN | WT | 245.9 | COD | 2011-01-24 | 2011-03-18 | 2011-09-12 |  | 2018-03-15 | No | Not Required | Not Required | Not Required
14INR0030c | Panhandle Wind 3 | SS Completed, FIS Started, IA | Pattern Energy | 79005 Railhead 345kV | Carson | PANHANDLE | 2020-12-01 | WIN | WT | 248 |  | 2012-07-03 | 2012-08-17 | 2014-03-26 |  | 2014-08-25 | Yes | Not Required | Not Required | Not Required | 1899-12-31 |  | 1899-12-31
14INR0033 | Goodnight Wind | SS Completed, FIS Completed, IA | FGE Power | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | PANHANDLE | 2019-08-11 | WIN | WT | 496.8 |  | 2012-07-24 | 2012-09-19 | 2013-03-04 | 2017-09-25 | 2018-03-07 | No | Not Required | Not Required | Not Required
14INR0044 | West of Pecos Solar | SS Completed, FIS Started, IA | Eon | 1094 Mason 138kV | Reeves | WEST | 2019-12-15 | SOL | PV | 100 |  | 2013-01-21 | 2013-02-19 | 2013-06-12 |  | 2017-02-27 | Yes | Not Required | Not Required | Not Required | 2017-05-04 |  | 2017-05-04
14INR0045 | Torrecillas Wind | SS Completed, FIS Completed, IA | Nextera | 161252, 161301 Torrecillas 34.5kV | Webb | SOUTH | 2019-03-01 | WIN | WT | 300.5 | COD SFS/NtP | 2013-01-30 | 2013-03-14 | 2013-01-30 | 2018-05-14 | 2018-04-12 | Yes | Not Required | Not Required | Not Required | 2018-04-26 | 2018-04-26 | 2018-04-26 |  |  | 2018-11-09
15INR0034 | El Algodon Alto W | SS Completed, FIS Started, No IA | Eon | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | COASTAL | 2020-12-31 | WIN | WT | 201 |  | 2013-02-04 | 2013-03-25 | 2013-08-16 |  |  | No | Not Required | Not Required | Not Required
15INR0044 | Corazon Solar | SS Completed, FIS Started, No IA | Enerverse | 80219 Lobo 345kV | Webb | SOUTH | 2019-12-31 | SOL | PV | 200 |  | 2013-09-06 | 2013-09-16 | 2013-08-20 |  |  | No | Not Required | Not Required | Not Required
15INR0051 | Tierra Blanca W | SS Completed, FIS Started, No IA | Eon | 79501 Ogallala 345kV | Randall | PANHANDLE | 2019-12-15 | WIN | WT | 200 |  | 2013-10-01 | 2013-10-18 | 2014-02-05 |  |  | No | Not Required | Not Required | Not Required
15INR0059 | Emerald Grove Solar | SS Completed, FIS Started, IA | Cypress Creek Renewables | 6601 Rio Pecos 138kV | Pecos | WEST | 2019-12-01 | SOL | PV | 108 |  | 2013-11-13 | 2013-12-23 | 2013-11-12 |  | 2018-06-27 | Yes | Not Required | Not Required | Not Required | 1899-12-31 |  | 1899-12-31
15INR0062 | Hale Community W 1 | SS Completed, FIS Started, No IA | Nextera | 79506 Abernathy 345kV | Hale | PANHANDLE | 2020-12-31 | WIN | WT | 322 |  | 2013-11-27 | 2014-01-27 | 2014-04-15 |  |  | No | Not Required | Not Required | Not Required
15INR0063 | Easter Wind | SS Completed, FIS Completed, IA | TriGlobal | 79502 Windmill 345kV | Castro | PANHANDLE | 2020-10-31 | WIN | WT | 307.5 |  | 2013-12-18 | 2014-02-27 | 2014-04-15 | 2017-12-06 | 2018-06-01 | No | Not Required | Not Required | Not Required
15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2019-10-04 | WIN | WT | 162.1 |  | 2013-11-27 | 2014-01-27 | 2014-04-15 | 2017-09-27 | 2018-05-30 | Yes | Not Required | Not Required | Not Required | 2018-05-30 | 2018-09-19 | 2018-05-30
15INR0090 | Pflugerville Solar | SS Completed, FIS Started, IA | RRE Solar | tap 138kV 7336 Gillie - 3650 Elgin | Travis | SOUTH | 2019-12-31 | SOL | PV | 144 |  | 2015-04-28 | 2015-07-01 | 2015-09-30 |  | 2017-06-13 | No | Not Required | Not Required | Not Required
16INR0003 | LEVEE (Freeport LNG) | SS Completed, FIS Completed, IA | Freeport LNG | 43336 Oyster Cr 138kV | Brazoria | COASTAL | 2019-08-01 | GAS | GT | 11 |  | 2011-12-15 | 2012-02-15 | 2012-01-04 | 2018-01-22 | 2014-01-13 | Yes | 2014-07-16 | Not Required |  | 2018-10-09 | 2018-10-09 | 2018-10-09
16INR0010 | FGE Texas 1 Gas | SS Completed, FIS Started, IA | FGE Power | Tap 345kV 1030 Morgan - 1025 Falcon | Mitchell | WEST | 2021-04-30 | GAS | CC | 742.9 |  | 2013-04-24 | 2013-05-29 | 2013-05-14 |  | 2016-08-31 | No | 2016-12-16 | 2016-12-12 | 2014-01-29
16INR0012 | Stella 2 Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 80076 Ajo - 80071 Zorillo | Kenedy | COASTAL | 2020-12-30 | WIN | WT | 201 | COD | 2013-06-13 | 2013-03-15 | 2013-09-10 |  |  | No | Not Required | Not Required | Not Required
16INR0014 | Cattleman Wind A | SS Completed, FIS Started, No IA | Eon | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | PANHANDLE | 2021-09-01 | WIN | WT | 201.6 |  | 2013-10-01 | 2013-11-18 | 2014-02-10 |  |  | No | Not Required | Not Required | Not Required
16INR0014b | Cattleman Wind B | SS Completed, FIS Started, No IA | Eon | tap 345kV 79501 Ogallala - 79502 Windmill | Castro | PANHANDLE | 2021-09-01 | WIN | WT | 201.6 | COD | 2013-10-01 | 2013-11-18 | 2014-02-10 |  |  | No | Not Required | Not Required | Not Required
16INR0019 | BlueBell Solar | SS Completed, FIS Completed, IA | Nextera | 76090 Divide 345kV | Coke | WEST | 2019-01-31 | SOL | PV | 30 | COD | 2013-11-15 | 2013-12-30 | 2013-11-07 | 2018-05-01 | 2015-08-19 | Yes | Not Required | Not Required | Not Required | 2018-05-01 | 2018-09-12 | 2018-05-01 |  |  | 2018-10-12 | 2018-10-25
16INR0033 | Hart Wind | SS Completed, FIS Completed, IA | Orion | 79501 Ogallala 345kV | Castro | PANHANDLE | 2020-12-31 | WIN | WT | 150 |  | 2014-02-10 | 2014-03-20 | 2014-10-27 | 2018-02-19 | 2018-08-06 | No | Not Required | Not Required | Not Required
16INR0037c | Pumpkin Farm Wind | SS Completed, FIS Completed, IA | Apex Clean | 79505 White River 345kV | Floyd | PANHANDLE | 2019-12-01 | WIN | WT | 280.9 |  | 2014-02-24 | 2014-04-08 | 2014-02-18 | 2018-01-12 | 2017-03-24 | Yes | Not Required | Not Required | Not Required | 2017-03-24 | 2018-09-19 | 2017-03-24
16INR0044 | Halyard Wharton | SS Completed, FIS Started, IA | Halyard Energy | tap 345kV 9073 Holman - 44200 Hillje | Wharton | SOUTH | 2021-06-01 | GAS | GT | 397.8 |  | 2014-03-17 | 2014-04-28 | 2014-11-11 |  | 2016-01-26 | No | 2015-10-09 | Not Required | 2015-09-21
16INR0045 | Halyard Henderson | SS Completed, FIS Started, IA | Halyard Energy | tap 345kV 3109 Stryker - 3123 Trinidad | Henderson | NORTH | 2021-05-01 | GAS | GT | 484 |  | 2014-03-20 | 2014-04-15 | 2014-07-21 |  | 2016-04-01 | No | 2015-12-08 | Not Required | 2016-01-05
16INR0049 | Nazareth Solar | SS Completed, FIS Started, IA | Lendlease Energy | 79501 Ogallala 345kV | Castro | PANHANDLE | 2020-05-01 | SOL | PV | 201 |  | 2014-06-19 | 2014-07-25 | 2014-07-01 |  | 2018-05-10 | No | Not Required | Not Required | Not Required
16INR0054 | NA | SS Completed, FIS Completed, IA | NASA | 42970 Nasa 138kV | Harris | HOUSTON | 2018-09-01 | GAS | CC | 12 |  | 2015-03-10 | 2015-04-01 | 2015-03-10 | 2016-01-26 | 2016-10-27 | Yes | Not Required | Not Required |  | 2016-11-10 | 2018-09-28 | 2016-11-10 |  |  |  | 2017-11-27
16INR0062b | Lockett Wind | SS Completed, FIS Completed, IA | Lincoln Clean | 141355-6 Electra 34.5kV | Wilbarger | WEST | 2019-09-30 | WIN | WT | 184 |  | 2014-09-15 | 2014-12-10 | 2014-12-05 | 2018-10-31 | 2015-03-31 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31
16INR0074 | Chocolate Bayou W | SS Completed, FIS Started, No IA | Engie | tap 138kV 42090 Amoco - 42940 Monsanto | Brazoria | COASTAL | 2019-12-01 | WIN | WT | 149.5 |  | 2014-12-08 | 2015-03-02 | 2014-12-04 |  |  | No | Not Required | Not Required | Not Required
16INR0076 | Hudson (Ineos/Brazoria) | SS Completed, FIS Completed, IA | Ineos | 42100 Hudson 138kV | Brazoria | COASTAL | 2019-01-31 | GAS | GT | 96 |  | 2015-01-12 | 2015-03-19 | 2015-06-24 | 2017-08-24 | 2017-12-05 | Yes | 2017-02-10 | 2017-02-10 | 2018-01-10 | 2018-10-09 |  | 2018-10-09
16INR0081 | Mesteno Wind | SS Completed, FIS Completed, IA | Duke Energy | 80355 Del Sol 345kV | Starr | SOUTH | 2019-11-30 | WIN | WT | 201.6 |  | 2014-12-30 | 2015-03-09 | 2014-12-30 | 2018-01-29 | 2018-04-25 | Yes | Not Required | Not Required | Not Required | 2018-04-25 |  | 2018-04-25
16INR0085 | Priddy Wind | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1444 Brown – 3422 Killeen | Mills | NORTH | 2020-12-31 | WIN | WT | 300 |  | 2015-01-14 | 2015-02-10 | 2015-03-06 |  |  | No | Not Required | Not Required | Not Required
16INR0086 | Cactus Flats Wind | SS Completed, FIS Completed, IA | Southern Power Company | tap 138kV 6480 SAPS - 6365 Yellow Jacket | Concho | WEST | 2018-12-15 | WIN | WT | 148.4 |  | 2015-02-02 | 2015-03-27 | 2015-02-02 | 2017-10-20 | 2017-03-15 | Yes | Not Required | Not Required | Not Required | 1899-12-31 | 2018-09-05 16:19 | 1899-12-31 |  |  | 2018-05-24 | 2018-06-11
16INR0097 | Morada Del Sol Solar | SS Completed, FIS Started, No IA | First Solar | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Upton | WEST | 2020-03-31 | SOL | PV | 245 |  | 2015-03-31 | 2015-06-23 | 2015-03-31 |  |  | No | Not Required | Not Required | Not Required
16INR0099 | Hecate Solar | SS Completed, FIS Started, No IA | Hecate Energy | tap 69kV 6653 Barilla - 6665 Alpine REA | Brewster | WEST | 2020-12-31 | SOL | PV | 33 |  | 2015-03-27 | 2015-05-14 | 2015-03-27 |  |  | No | Not Required | Not Required | Not Required
16INR0101 | Chatee Solar | SS Completed, FIS Started, No IA | Hecate Energy | 6641 Sun Valley 69kV | Pecos | WEST | 2020-12-31 | SOL | PV | 57 |  | 2015-04-07 | 2015-05-14 | 2015-04-07 |  |  | No | Not Required | Not Required | Not Required
16INR0102 | Owego Solar | SS Completed, FIS Started, No IA | Hecate Energy | 6601 Rio Pecos 138kV | Pecos | WEST | 2020-12-31 | SOL | PV | 74 |  | 2015-04-07 | 2015-05-14 | 2015-04-07 |  |  | No | Not Required | Not Required | Not Required
16INR0104 | Big Sampson Wind | SS Completed, FIS Completed, No IA | Infinity Renewables | 76005 Schneeman Draw 345kV | Crockett | WEST | 2019-12-01 | WIN | WT | 400 |  | 2015-05-11 | 2015-06-17 | 2015-05-11 | 2018-12-11 |  | No | Not Required | Not Required | Not Required
16INR0105 | Zapata I W | SS Completed, FIS Started, No IA | Nextera | 8299 Zapata 138kV | Jim Hogg | SOUTH | 2019-12-01 | WIN | WT | 300 |  | 2015-04-30 | 2015-05-26 | 2015-04-30 |  |  | No | Not Required | Not Required | Not Required
16INR0106 | Whatley Solar | SS Completed, FIS Started, No IA | Invenergy | 1281 Amoco Midland tap 69kV | Andrews | WEST | 2020-12-31 | SOL | PV | 150 |  | 2015-05-05 | 2015-05-26 | 2015-09-22 |  |  | No | Not Required | Not Required | Not Required
16INR0111 | Las Lomas Wind | SS Completed, FIS Started, No IA | Enerverse | 8957 Lopeno 138kV | Starr | SOUTH | 2019-12-31 | WIN | WT | 200 |  | 2015-05-18 | 2015-06-25 | 2015-05-18 |  |  | No | Not Required | Not Required | Not Required
16INR0112 | Loma Pinta Wind | SS Completed, FIS Completed, IA | Enerverse | 5705 Fowlerton 138kV | La Salle | SOUTH | 2019-11-30 | WIN | WT | 200 |  | 2015-05-18 | 2015-07-02 | 2015-05-18 | 2017-03-24 | 2017-12-13 | No | Not Required | Not Required | Not Required
16INR0114 | Upton Solar | SS Completed, FIS Started, IA | Clearway Energy | 76020 SONNE 138-kV | Upton | WEST | 2020-05-31 | SOL | PV | 104.56 | MW Size COD SFS/NtP | 2015-05-27 | 2015-07-02 | 2015-06-08 |  | 2015-12-04 | Yes | Not Required | Not Required | Not Required | 2018-12-14 |  | 2018-12-14
16INR0117 | Tecovas 1 W | SS Completed, FIS Started, No IA | Engie | 79503 Tule Canyon 345kV | Briscoe | PANHANDLE | 2020-06-01 | WIN | WT | 200 |  | 2015-06-23 | 2015-07-06 | 2015-10-19 |  |  | No | Not Required | Not Required | Not Required
16INR0119 | Wake Solar | SS Completed, FIS Started, No IA | Invenergy | 59904 Cottonwood 345kV | Crosby | PANHANDLE | 2021-12-31 | SOL | PV | 150 |  | 2015-07-20 | 2015-07-27 | 2015-10-05 |  |  | No | Not Required | Not Required | Not Required
17INR0005 | Cabezon Wind | SS Completed, FIS Completed, IA | Longroad Energy | 80355 Del Sol 345kV | Starr | SOUTH | 2019-04-01 | WIN | WT | 237.6 |  | 2013-09-17 | 2013-10-25 | 2013-09-06 | 2017-12-22 | 2017-08-03 | Yes | Not Required | Not Required | Not Required | 2017-12-08 | 2018-09-12 | 2017-12-08
17INR0010 | FGE Texas 2 Gas | SS Completed, FIS Started, IA | FGE Power | Tap 345kV 1030 Morgan – 1058 Longshore | Mitchell | WEST | 2022-05-25 | GAS | CC | 742.9 |  | 2014-02-11 | 2014-03-26 | 2014-02-19 |  | 2015-06-02 | No | 2016-12-16 | 2016-12-12
17INR0020a | RE Maplewood 2a Solar | SS Completed, FIS Started, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2019-12-31 | SOL | PV | 100 |  | 2014-10-17 | 2014-12-01 | 2014-10-22 |  | 2016-02-03 | Yes | Not Required | Not Required | Not Required | 2018-03-19 |  | 2018-03-19
17INR0020b | RE Maplewood 2b Solar | SS Completed, FIS Started, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2019-12-31 | SOL | PV | 100 |  | 2014-10-17 | 2014-12-01 | 2014-10-22 |  | 2016-02-03 | Yes | Not Required | Not Required | Not Required | 2018-03-19 |  | 2018-03-19
17INR0020c | RE Maplewood 2c Solar | SS Completed, FIS Started, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2019-12-31 | SOL | PV | 100 |  | 2014-10-17 | 2014-12-01 | 2014-10-22 |  | 2016-02-03 | Yes | Not Required | Not Required | Not Required | 2018-03-19 |  | 2018-03-19
17INR0020d | RE Maplewood 2d Solar | SS Completed, FIS Started, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2020-12-31 | SOL | PV | 100 |  | 2014-10-17 | 2014-12-01 | 2014-10-22 |  | 2016-02-03 | Yes | Not Required | Not Required | Not Required | 2018-03-19 |  | 2018-03-19
17INR0020e | RE Maplewood 2e Solar | SS Completed, FIS Started, IA | Recurrent Energy | 76002 Bakersfield 345kV | Pecos | WEST | 2020-12-31 | SOL | PV | 100 |  | 2014-10-17 | 2014-12-01 | 2014-10-22 |  | 2016-02-03 | Yes | Not Required | Not Required | Not Required | 2018-03-19 |  | 2018-03-19
17INR0022 | MIRAGE | SS Completed, FIS Completed, IA | Net Power | 111161 Mirage 13.8kV | Harris | HOUSTON | 2019-02-18 | GAS | GT | 11 |  | 2015-02-17 | 2015-05-01 | 2015-05-20 | 2016-09-13 | 2016-08-31 | Yes | Not Required | Not Required | 2017-10-12 | 2016-10-11 | 2018-09-28 | 2016-10-11 |  |  | 2017-02-06
17INR0025 | Reloj Del Sol Wind | SS Completed, FIS Started, No IA | EDP Renewables | 80220 Cenizo 345kV | Zapata | SOUTH | 2020-10-31 | WIN | WT | 202 |  | 2015-03-24 | 2015-05-05 | 2015-09-14 |  |  | No | Not Required | Not Required | Not Required
17INR0027b | Coyote Wind | SS Completed, FIS Started, IA | Coyote Wind | 11305 Dermott 345kV | Scurry | WEST | 2020-06-03 | WIN | WT | 242.5 |  | 2015-04-22 | 2015-05-22 | 2015-06-11 |  | 2016-08-09 | Yes | Not Required | Not Required | Not Required | 2016-08-09 |  | 2016-08-09
17INR0030 | Estacado Solar | SS Completed, FIS Started, No IA | Avangrid | 79502 Windmill 345kV | Deaf Smith | PANHANDLE | 2019-12-31 | SOL | PV | 100 |  | 2015-05-12 | 2015-06-01 | 2015-11-24 |  |  | No | Not Required | Not Required | Not Required
17INR0031 | Espiritu Wind | SS Completed, FIS Started, No IA | Acciona | 5764 E Rio Hondo 138kV | Cameron | COASTAL | 2019-12-31 | WIN | WT | 148.5 |  | 2015-05-19 | 2015-06-22 | 2015-10-26 |  |  | No | Not Required | Not Required | Not Required
17INR0033 | Tecovas 2 W | SS Completed, FIS Started, No IA | Engie | 79503 Tule Canyon 345kV | Briscoe | PANHANDLE | 2020-06-01 | WIN | WT | 200 |  | 2015-06-23 | 2015-07-06 | 2015-10-19 |  |  | No | Not Required | Not Required | Not Required
17INR0035 | Las Majadas Wind | SS Completed, FIS Started, IA | EDF Renewable Energy | 8318 Rio Hondo 345kV plus 12.5mi gentie | Willacy | COASTAL | 2020-10-01 | WIN | WT | 272.8 |  | 2015-10-30 | 2015-12-14 | 2015-12-09 |  | 2018-04-13 | No | Not Required | Not Required | Not Required
17INR0036 | Grandview 4 Phase A Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 79000 Gray - 79006 Allen | Carson | PANHANDLE | 2019-12-01 | WIN | WT | 200.5 |  | 2015-11-25 | 2016-01-11 | 2016-01-21 |  |  | No | Not Required | Not Required | Not Required
17INR0037 | Palmas Altas Wind | SS Completed, FIS Completed, IA | Acciona | 5760 PALMAS 138 kV | Cameron | COASTAL | 2019-08-01 | WIN | WT | 144.9 |  | 2016-03-24 | 2016-05-06 | 2016-07-20 | 2018-08-07 | 2017-11-30 | Yes | Not Required | Not Required | Not Required | 2018-10-04 | 2018-10-04 | 2018-10-04
17INR0038 | Zapata II W | SS Completed, FIS Started, No IA | Nextera | 80220 Cenizo 345kV | Zapata | SOUTH | 2019-12-31 | WIN | WT | 400 |  | 2016-01-05 | 2016-02-15 | 2016-01-05 |  |  | No | Not Required | Not Required | Not Required
17INR0043 | Vaquero 1 Wind | SS Completed, FIS Started, No IA | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Zapata | SOUTH | 2020-12-31 | WIN | WT | 400 |  | 2016-04-01 | 2016-05-10 | 2016-04-01 |  |  | No | Not Required | Not Required | Not Required
17INR0045 | VictPort | SS Completed, FIS Completed, IA | Castleman Power | 8143 Dupont 138kV | Calhoun | COASTAL | 2019-03-01 | GAS | GT | 100 |  | 2016-04-20 | 2016-06-10 | 2017-01-10 | 2018-06-15 | 2018-03-06 | Yes | Not Required | Not Required | 2018-05-01 | 2017-03-06 | 2018-09-19 | 2017-03-06
17INR0052 | Horse13 CallD repower | SS Completed, FIS Completed, No IA | Nextera | 6216 Bluff Creek 138kV | Taylor | WEST | 2018-11-01 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2018-04-10 |  | No | Not Required | Not Required | Not Required
17INR0053 | HHGT repower Horse13+CallD | SS Completed, FIS Completed, No IA | Nextera | 7046 Kendal 345kV | Taylor | WEST | 2018-11-01 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2017-07-06 |  | No | Not Required | Not Required | Not Required
17INR0054 | Capricorn I & III repower | SS Completed, FIS Completed, No IA | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WEST | 2018-11-01 | WIN | WT | 32 |  | 2017-03-09 | 2017-04-24 | 2017-03-09 | 2018-02-26 |  | No | Not Required | Not Required | Not Required
17INR0056 | Callahan repower | SS Completed, FIS Completed, No IA | Nextera |  | Taylor | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-07-19 | 2017-09-15 | 2017-07-19 | 2017-08-14 |  | No | Not Required | Not Required | Not Required
17INR0057 | Red Canyon repower | SS Completed, FIS Completed, No IA | Nextera | 729 ScurrySw 138kV | Garza | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-07-21 | 2017-09-15 | 2017-07-21 | 2017-10-13 |  | No | Not Required | Not Required | Not Required
17INR0058 | Horse Hollow II repower | SS Completed, FIS Completed, No IA | Nextera | Bluff Creek 138kV | Taylor | WEST | 2019-03-01 | WIN | WT | 0 | COD | 2017-07-28 | 2017-09-15 | 2017-07-28 | 2017-12-12 |  | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 12:38 | 2018-10-31
17INR0060 | Horse Hollow IV repower | SS Completed, FIS Completed, No IA | Nextera |  | Taylor | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-07-28 | 2017-09-15 | 2017-07-28 | 2017-12-12 |  | No | Not Required | Not Required | Not Required
17INR0061 | Capricorn IV repower | SS Completed, FIS Completed, No IA | Nextera |  | Sterling | WEST | 2018-11-01 | WIN | WT | 9 |  | 2017-08-23 | 2017-09-15 | 2017-08-23 | 2018-02-06 |  | No | Not Required | Not Required | Not Required
17INR0063 | Capricorn I repower | SS Completed, FIS Completed, No IA | Nextera |  | Sterling | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-08-16 | 2017-09-15 | 2017-08-16 | 2017-11-08 |  | No | Not Required | Not Required | Not Required
17INR0064 | Capricorn II repower | SS Completed, FIS Completed, No IA | Nextera |  | Sterling | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-08-16 | 2017-09-15 | 2017-08-16 | 2017-12-12 |  | No | Not Required | Not Required | Not Required
17INR0065 | Capricorn III repower | SS Completed, FIS Completed, No IA | Nextera |  | Sterling | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-08-16 | 2017-09-15 | 2017-08-16 | 2017-11-08 |  | No | Not Required | Not Required | Not Required
17INR0067 | Sweetwater 1 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2019-03-01 | WIN | WT | 0 | COD | 2017-10-03 | 2017-10-03 | 2017-10-03 | 2017-10-11 | 1899-12-31 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31
17INR0068 | Sweetwater 2 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2019-03-01 | WIN | WT | 7.3 | COD | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-11-10 | 2017-11-17 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 12:42 | 2018-10-31 |  |  |  | 2017-12-20
17INR0069 | Trent repower | SS Completed, FIS Completed, IA | Invenergy | 1338 Eskota 138kV | Nolan | WEST | 2019-03-01 | WIN | WT | 6.4 | COD | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-03-01 | 2018-10-19 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 11:50 | 2018-10-31
17INR0070 | Desert Sky repower | SS Completed, FIS Completed, IA | Invenergy | two LCRA 138kV | Pecos | WEST | 2019-03-01 | WIN | WT | 7.2 | COD | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-02-06 | 2018-10-18 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31
17INR0101 | Horse 1 repower | SS Completed, FIS Completed, No IA | Nextera |  | Taylor | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 |  | No | Not Required | Not Required | Not Required
17INR0103 | Horse 3 repower | SS Completed, FIS Completed, No IA | Nextera |  | Taylor | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 |  | No | Not Required | Not Required | Not Required
17INR0104 | Capricorn 4 repower | SS Completed, FIS Completed, IA | Nextera |  | Coke | WEST | 2018-11-01 | WIN | WT | 0 |  | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2018-05-01 | No | Not Required | Not Required | Not Required
18INR0009 | Eagle Pines Gas | SS Completed, FIS Started, No IA | FGE Power | tap 345kV 3109 Stryker - 3123 Trinidad | Cherokee | NORTH | 2021-02-15 | GAS | CC | 1173.5 |  | 2015-03-30 | 2015-06-23 | 2015-04-29 |  |  | No | 2017-02-14 | 2015-11-04
18INR0014 | Karankawa Wind | SS Completed, FIS Completed, IA | Avangrid | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | COASTAL | 2019-12-31 | WIN | WT | 200 |  | 2015-10-28 | 2015-11-11 | 2016-05-04 | 2018-08-03 | 2017-11-30 | Yes | Not Required | Not Required | Not Required | 2017-11-30 |  | 2017-11-30
18INR0016 | RTS 2 Wind | SS Completed, FIS Started, IA | RES Americas | 76006 Bow Wood 345kV | McCulloch | SOUTH | 2020-06-30 | WIN | WT | 179.91 | MW Size | 2015-11-02 | 2015-12-07 | 2015-12-31 |  | 2017-11-21 | Yes | Not Required | Not Required | Not Required
18INR0018 | Peyton Creek Wind | SS Completed, FIS Completed, IA | Eon | tap 345kV 5915 STP - 42500 Dow | Matagorda | COASTAL | 2019-12-01 | WIN | WT | 151.2 |  | 2015-11-25 | 2015-12-22 | 2016-06-22 | 2017-07-24 | 2018-03-19 | Yes | Not Required | Not Required | Not Required | 2018-03-19 | 2018-09-19 14:15 | 2018-03-19
18INR0023 | Darmstadt | SS Completed, FIS Completed, IA | RES Americas | 60708 Orsted 345kV - Big Hill | Schleicher | WEST | 2019-12-31 | WIN | WT | 200.9 |  | 2016-06-07 | 2016-09-04 | 2016-10-07 | 2018-07-23 | 2018-05-11 | No | Not Required | Not Required | Not Required
18INR0025 | Tahoka Wind | SS Completed, FIS Completed, IA | Lincoln Clean | 79641 Farmland 345kV | Lynn | WEST | 2019-01-02 | WIN | WT | 300 |  | 2016-03-14 | 2016-03-23 | 2016-04-22 | 2017-11-29 | 2018-01-03 | Yes | Not Required | Not Required | Not Required | 2018-01-03 | 2018-09-28 | 2018-01-03 |  |  | 2018-11-02 | 2018-11-09
18INR0027 | Ponwar Solar Farm | SS Completed, FIS Started, No IA | 8minutenergy | tap 138kV 76032 N McCamey - 60361 Santa Rita | Upton | WEST | 2019-10-01 | SOL | PV | 180 |  | 2016-04-06 | 2016-05-27 | 2016-10-27 |  |  | No | Not Required | Not Required | Not Required
18INR0029 | Armstrong Wind | SS Completed, FIS Completed, IA | Big Sky Energy | tap 345kV 79500 Alibates - 79503 Tule Canyon | Armstrong | PANHANDLE | 2020-03-31 | WIN | WT | 253 |  | 2016-05-10 | 2016-05-24 | 2016-07-25 | 2018-01-25 | 2018-08-31 | No | Not Required | Not Required | Not Required
18INR0030 | Canyon Wind | SS Completed, FIS Started, IA | TriGlobal | 11319 ScurryCounty 138kV | Scurry | WEST | 2020-06-30 | WIN | WT | 360 |  | 2016-05-09 | 2016-07-22 | 2017-03-02 |  | 2018-09-20 | No | Not Required | Not Required | Not Required
18INR0031 | Maryneal Wind | SS Completed, FIS Started, No IA | Duke Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2020-11-30 | WIN | WT | 180 |  | 2016-05-26 | 2016-07-21 | 2016-07-22 |  |  | No | Not Required | Not Required | Not Required
18INR0033 | Oveja Wind | SS Completed, FIS Completed, IA | Invenergy | 76005 Schneeman Draw 345kV | Irion | WEST | 2019-06-30 | WIN | WT | 300 |  | 2016-07-12 | 2016-09-07 | 2016-10-21 | 2018-07-11 | 2018-07-24 | Yes | Not Required | Not Required | Not Required | 2018-07-30 | 2018-09-28 | 2018-07-30
18INR0034 | Blanco Canyon Wind | SS Completed, FIS Started, No IA | Invenergy | 59904 Cottonwood 345kV | Crosby | PANHANDLE | 2021-12-31 | WIN | WT | 250.7 |  | 2016-07-21 | 2016-09-14 | 2017-03-22 |  |  | No | Not Required | Not Required | Not Required
18INR0035 | CityVict | SS Completed, FIS Completed, IA | Castleman Power | 8172 Victoria 138kV | Refugio | COASTAL | 2019-04-01 | GAS | GT | 100 |  | 2016-08-15 | 2016-09-27 | 2017-03-27 | 2018-07-25 | 2018-03-06 | Yes | Not Required | Not Required | 2018-04-26 | 2018-03-06 | 2018-09-19 | 2018-03-06
18INR0038 | Barrow Ranch | SS Completed, FIS Completed, IA | Engie | 1134 Littman 138kV | Andrews | WEST | 2019-12-01 | WIN | WT | 160 |  | 2016-10-02 | 2016-12-12 | 2017-06-19 | 2018-05-09 | 2018-06-26 | Yes | Not Required | Not Required | Not Required | 2018-09-04 |  | 2018-09-04
18INR0039 | Fowler Ranch | SS Completed, FIS Started, No IA | Solar Prime | tap 138kV 60014 Spudder - 76615 Crane | Crane | WEST | 2020-04-30 | SOL | PV | 150 |  | 2016-10-07 | 2016-11-08 | 2016-12-23 |  |  | No | Not Required | Not Required | Not Required
18INR0040 | Soda Lake Solar 1 | SS Completed, FIS Started, IA | Arrington Solar | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | WEST | 2020-07-01 | SOL | PV | 200 |  | 2016-10-07 | 2016-11-08 | 2017-02-10 |  | 2018-08-20 | No | Not Required | Not Required | Not Required
18INR0042 | Kaiser Creek Wind | SS Completed, FIS Started, No IA | Calpine | Tap 138kV 6275 Abilene East – 6670 Putnam | Callahan | WEST | 2020-10-01 | WIN | WT | 100 |  | 2016-10-12 | 2016-12-01 | 2016-10-07 |  |  | No | Not Required | Not Required | Not Required
18INR0043 | Edmondson Ranch Wind | SS Completed, FIS Completed, IA | Wind Tex | 59903 Bearkat 345kV | Glasscock | WEST | 2020-06-26 | WIN | WT | 292.5 |  | 2016-10-26 | 2016-12-22 | 2017-02-01 | 2018-01-30 | 2017-10-04 | Yes | Not Required | Not Required | Not Required | 1899-12-31 | 2018-09-05 | 1899-12-31
18INR0044 | Bluegrove Wind | SS Completed, FIS Started, No IA | Innergex | tap 138kV 1468 LKAROWHD - 1470 NEWPRT_P | Clay | WEST | 2019-12-31 | WIN | WT | 100 |  | 2016-10-19 | 2016-12-06 | 2017-02-02 |  |  | No | Not Required | Not Required | Not Required
18INR0045 | Misae Solar | SS Completed, FIS Started, IA | CIP | 60501 Tesla 345kV | Childress | PANHANDLE | 2019-11-29 | SOL | PV | 240.8 |  | 2016-10-20 | 2017-01-06 | 2016-10-20 |  | 2018-07-18 | Yes | Not Required | Not Required | Not Required
18INR0049 | Santa Rita Solar | SS Completed, FIS Started, No IA | Invenergy | 76005 Schneeman Draw 345kV | Crockett | WEST | 2022-12-31 | SOL | PV | 400 |  | 2016-11-09 | 2016-12-19 | 2017-05-30 |  |  | No | Not Required | Not Required | Not Required
18INR0050 | Mustang Creek Solar | SS Completed, FIS Completed, No IA | Sunchase Power | 5523 ETP 138kV | Jackson | SOUTH | 2019-12-01 | SOL | PV | 150 |  | 2016-11-16 | 2016-12-20 | 2017-03-22 | 2018-10-03 |  | No | Not Required | Not Required | Not Required
18INR0051 | Byers Wind | SS Completed, FIS Started, No IA | Innergex | tap 345kV 6101 Riley - 1730 W Krum | Clay | WEST | 2019-12-31 | WIN | WT | 200 |  | 2016-11-28 | 2016-12-15 | 2017-01-30 |  |  | No | Not Required | Not Required | Not Required
18INR0053 | Fort Bend Solar | SS Completed, FIS Started, No IA | Lendlease Energy | tap 138kV 44541 Orchard - 44190 E Bernard | Fort Bend | HOUSTON | 2020-03-01 | SOL | PV | 240 |  | 2016-12-19 | 2017-02-15 | 2017-09-08 |  |  | No | Not Required | Not Required | Not Required
18INR0055 | Long Draw Solar | SS Completed, FIS Started, IA | ENGIE | 59900 Long Draw 345kV | Borden | WEST | 2020-06-30 | SOL | PV | 225 |  | 2016-12-15 | 2017-02-02 | 2017-02-28 |  | 2018-08-16 | Yes | Not Required | Not Required | Not Required
18INR0056 | Hallmark Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 69kV 1824 Neyland - 1826 Cadmil | Hunt | NORTH | 2019-10-31 | SOL | PV | 43 |  | 2016-12-15 | 2017-02-16 | 2017-02-21 |  |  | No | Not Required | Not Required | Not Required
18INR0058 | Texana Solar | SS Completed, FIS Started, No IA | Sunchase Power | tap 138kV 8102 El Campo - 8117 Ganado | Wharton | SOUTH | 2021-03-01 | SOL | PV | 150 |  | 2016-12-23 | 2017-02-14 | 2017-03-22 |  |  | No | Not Required | Not Required | Not Required
18INR0059 | Raymond Wind | SS Completed, FIS Started, IA | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2019-12-30 | WIN | WT | 201.6 | COD | 2017-01-27 | 2017-03-09 | 2017-02-10 |  | 2018-09-18 | Yes | Not Required | Not Required | Not Required | 2018-10-17 |  | 2018-10-17
18INR0060 | Brightside Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 69kV 8198 Beeville - 8400 Three River | Bee | SOUTH | 2019-12-01 | SOL | PV | 50 |  | 2017-02-17 | 2017-03-20 | 2017-02-21 |  |  | No | Not Required | Not Required | Not Required
18INR0062 | Wagyu Solar | SS Completed, FIS Completed, No IA | Cypress Creek Renewables | tap 138kV 43380 West Columbia - 44010 WA Parish | Brazoria | COASTAL | 2020-06-01 | SOL | PV | 121.9 |  | 2017-02-22 | 2017-04-03 | 2017-02-22 | 2018-11-01 |  | No | Not Required | Not Required | Not Required
18INR0064 | Silver Star repower | SS Completed, FIS Completed, IA | BP | 1642 Flat Creek 138kV | Eastland | NORTH | 2019-11-01 | WIN | WT | -7.2 |  | 2017-04-05 | 2017-05-08 | 2017-07-06 | 2018-04-26 | 2018-10-16 | No | Not Required | Not Required | Not Required
18INR0065 | Goodranch Solar | SS Completed, FIS Started, No IA | EDF Renewable Energy | 79600 Vealmoor 138kV OR 79640 Vealmoor 345kV | Borden | WEST | 2020-12-01 | SOL | PV | 200 |  | 2017-06-23 | 2017-08-04 | 2018-04-02 |  |  | No | Not Required | Not Required | Not Required
18INR0067 | Gopher Creek Wind | SS Completed, FIS Completed, IA | Terna Energy | 11306 Dermott 138kV | Scurry | WEST | 2019-07-31 | WIN | WT | 158 |  | 2017-07-11 | 2017-08-28 | 2017-07-26 | 2018-01-26 | 2018-01-26 | Yes | Not Required | Not Required | Not Required | 1899-12-31 | 2018-09-06 | 1899-12-31
18INR0068 | Loraine Windpark Phase III | SS Completed, FIS Completed, IA | Third Planet Wind Power | 181153 Lonewolf 345kV | Mitchell | WEST | 2020-01-01 | WIN | WT | 100 | COD | 2017-08-14 | 2017-10-05 | 2017-10-20 | 2018-04-11 | 2018-04-10 | Yes | Not Required | Not Required | Not Required | 2018-04-12 | 2018-09-12 | 2018-04-12
18INR0069 | Indian Mesa repower | SS Completed, FIS Completed, IA | Nextera | 76019 Indian NWP 138kV | Pecos | WEST | 2019-01-01 | WIN | WT | 0 |  | 2018-05-22 | Date Not Available | 2018-05-22 | 2018-10-03 | 2018-12-04 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2018-11-02
18INR0070 | Blue Summit II | SS Completed, FIS Completed, IA | Nextera | 61001 Jim Treece 345kV | Wilbarger | WEST | 2019-01-15 | WIN | WT | 102 |  | 2017-11-02 | 2017-12-21 | 2017-11-02 | 2018-05-24 | 2018-04-28 | Yes | Not Required | Not Required | Not Required | 2018-05-07 | 2018-09-12 | 2018-05-07 |  |  | 2018-12-18
18INR0072 | Blue Summit repower | SS Completed, FIS Started, No IA | Nextera | 61001 Jim Treece 345kV | Wilbarger | WEST | 2019-06-03 | WIN | WT | 9.9 | COD | 2018-01-04 | 2018-01-04 | 2018-01-04 |  |  | No | Not Required | Not Required | Not Required
18INR0073 | Sweetwater 1 repower | SS Completed, FIS Completed, No IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2019-03-01 | WIN | WT | 3 | COD | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-12-27 |  | No | Not Required | Not Required | Not Required
18INR0075 | Gulf Wind 1 repower | SS Completed, FIS Started, No IA | Pattern Energy | 80071 Zorillo 345kV | Kenedy | COASTAL | 2019-02-28 | WIN | WT | 0 |  | 2018-03-05 | 2018-03-05 | 2018-03-05 |  |  | No | Not Required | Not Required | Not Required
18INR0076 | Wolf Hollow 2 repower | SS Completed, FIS Started, No IA | Exelon | 1877 Mitchell Bend 345kV | Hood | NORTH | 2019-04-16 | GAS | CC | 44 | COD | 2018-04-24 | 2018-04-24 | 2018-04-24 |  |  | No | Not Required | Not Required |  | 2018-10-31 | 2018-10-31 | 2018-10-31
18INR0077 | Colorado Bend 2 repower | SS Completed, FIS Started, No IA | Exelon | 44040 Bailey 345kV | Wharton | SOUTH | 2019-05-01 | GAS | CC | 45 | COD | 2018-04-24 | 2018-04-24 | 2018-04-24 |  |  | No | Not Required | Not Required |  | 2018-10-31 | 2018-10-31 12:40 | 2018-10-31
18INR0078 | Bobcat Bluff repower | SS Completed, FIS Completed, IA | EDF Renewable Energy | 1475 Windthorst 138kV | Archer | WEST | 2019-07-08 | WIN | WT | 12 | COD | 2018-05-15 | 2018-07-19 | 2018-05-15 | 2018-10-24 | 2018-12-18 | No | Not Required | Not Required | Not Required | [6 empty] | 2018-12-20
18INR0079 | Woodward I repower | SS Completed, FIS Started, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2019-01-01 | WIN | WT | 0 |  | 2018-06-27 | 2018-06-27 | 2018-06-27 |  | 2018-12-12 | No | Not Required | Not Required | Not Required | [6 empty] | 2018-12-18
18INR0080 | Woodward 2 repower | SS Completed, FIS Completed, No IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2018-12-31 | WIN | WT | 0 |  | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-11-27 |  | No | Not Required | Not Required | Not Required | [6 empty] | 2018-12-19
19INR0001 | Texas Solar Nova | SS Completed, FIS Started, No IA | SunPower | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2021-12-01 | SOL | PV | 750 |  | 2015-11-17 | 2015-12-30 | 2016-07-06 |  |  | No | Not Required | Not Required | Not Required
19INR0002 | King Mountain Solar | SS Completed, FIS Started, No IA | Nextera | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | WEST | 2021-05-01 | SOL | PV | 350 |  | 2016-05-24 | 2016-06-06 | 2016-05-24 |  |  | No | Not Required | Not Required | Not Required
19INR0006 | Bluebonnet Solar | SS Completed, FIS Started, No IA | One Energy Renewables | tap 138kV 6680 Alamito - 60385 Solstice | Brewster | WEST | 2019-11-01 | SOL | PV | 60.7 |  | 2016-07-18 | 2016-10-07 | 2017-04-05 |  |  | No | Not Required | Not Required | Not Required
19INR0007 | Charbray Solar | SS Completed, FIS Started, No IA | 8minutenergy | 1032 Morgan Creek 138kV | Mitchell | WEST | 2020-10-01 | SOL | PV | 200 |  | 2016-07-26 | 2016-10-07 | 2017-04-07 |  |  | No | Not Required | Not Required | Not Required
19INR0009 | Holstein Solar | SS Completed, FIS Started, IA | 8minutenergy | 11406 Central Bluff 345kV | Nolan | WEST | 2020-04-01 | SOL | PV | 204 |  | 2016-07-26 | 2016-09-13 | 2017-01-31 |  | 2018-09-15 | No | Not Required | Not Required | Not Required
19INR0014 | Formosa Increase | SS Completed, FIS Started, No IA | Formosa Plastics |  | Calhoun | COASTAL | 2019-12-31 | GAS | CC | 240 |  | 2016-09-12 | 2016-11-14 | 2017-06-08 |  |  | No | Not Required | Not Required
19INR0017 | Tri-County Solar | SS Completed, FIS Started, No IA | First Solar | tap 138kV 1027 Odessa - 1107 Monahans2T | Crane | WEST | 2020-12-31 | SOL | PV | 207 |  | 2016-10-10 | 2016-11-29 | 2017-02-22 |  |  | No | Not Required | Not Required | Not Required
19INR0019 | Foard City Wind | SS Completed, FIS Completed, IA | Innergex | 60500 Edith Clarke 345kV | Foard | WEST | 2019-09-01 | WIN | WT | 350 |  | 2016-10-19 | 2016-11-28 | 2017-01-11 | 2018-08-01 | 2018-02-19 | Yes | Not Required | Not Required | Not Required | 2018-06-22 | 2018-11-05 | 2018-06-22
19INR0020 | SP-Pecos Bend Solar A | SS Completed, FIS Started, No IA | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | WEST | 2020-05-15 | SOL | PV | 180 |  | 2016-10-26 | 2016-12-07 | 2016-10-31 |  |  | No | Not Required | Not Required | Not Required
19INR0020b | SP-Pecos Bend Solar B | SS Completed, FIS Started, No IA | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | WEST | 2020-05-15 | SOL | PV | 180 |  | 2016-10-26 | 2016-12-07 | 2016-10-31 |  |  | No | Not Required | Not Required | Not Required
19INR0020c | SP-Pecos Bend Solar C | SS Completed, FIS Started, No IA | Solar Prime | tap 345kV 76002 Bakersfield - 76005 SchneemanDr, ~ 11 mi E of Bakersfield. | Pecos | WEST | 2020-05-15 | SOL | PV | 180 |  | 2016-10-26 | 2016-12-07 | 2016-10-31 |  |  | No | Not Required | Not Required | Not Required
19INR0022 | West Willacy 2 W | SS Completed, FIS Started, No IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2019-12-31 | WIN | WT | 200 |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  |  | No | Not Required | Not Required | Not Required
19INR0023 | West Willacy 3 W | SS Completed, FIS Started, No IA | Terra-Gen | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2019-12-31 | WIN | WT | 200 |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  |  | No | Not Required | Not Required | Not Required
19INR0026 | Holstein 2 Solar | SS Completed, FIS Started, No IA | 8minutenergy | 11406 Central Bluff 345kV | Nolan | WEST | 2020-04-01 | SOL | PV | 100 |  | 2016-12-21 | 2017-02-02 | 2017-02-13 |  |  | No | Not Required | Not Required | Not Required
19INR0028 | Normande Solar Farm | SS Completed, FIS Started, No IA | 8minutenergy | 59900 Long Draw 345kV | Borden | WEST | 2019-12-01 | SOL | PV | 360 |  | 2017-01-30 | 2017-02-22 | 2017-08-24 |  |  | No | Not Required | Not Required | Not Required
19INR0029 | Phoebe Solar | SS Completed, FIS Completed, IA | Longroad Energy | 11260 Dune Switch | Winkler | WEST | 2019-09-01 | SOL | PV | 250 | COD | 2017-01-26 | 2017-02-15 | 2017-03-07 | 2018-10-23 | 2018-03-05 | Yes | Not Required | Not Required | Not Required | 2018-03-05 | 2018-09-14 | 2018-03-05
19INR0030 | San Bernard Solar | SS Completed, FIS Started, No IA | Sunchase Power | 43340 Tx Gulf Sulphur 138kV | Wharton | SOUTH | 2020-06-01 | SOL | PV | 100 |  | 2017-01-26 | 2017-04-12 | 2017-03-22 |  |  | No | Not Required | Not Required | Not Required
19INR0031 | Bestla Solar | SS Completed, FIS Started, No IA | Longroad Energy | tap 138kV 1147 Cheyenne - 131853 Notrees | Winkler | WEST | 2020-07-01 | SOL | PV | 180 |  | 2017-01-30 | 2017-03-06 | 2017-03-23 |  |  | No | Not Required | Not Required | Not Required
19INR0033 | Murphy Lake Solar | SS Completed, FIS Started, No IA | S Power | 6904 CombinRC 138kV | Kaufman | NORTH | 2019-12-01 | SOL | PV | 120 |  | 2017-02-06 | 2017-03-03 | 2017-08-10 |  |  | No | Not Required | Not Required | Not Required
19INR0034 | Greasewood Solar | SS Completed, FIS Started, No IA | Onpeak Power | tap 345kV 76002 Bakersfield - 76000 NMcCamey | Pecos | WEST | 2020-04-30 | SOL | PV | 200 |  | 2017-02-22 | 2017-04-17 | 2017-10-10 |  |  | No | Not Required | Not Required | Not Required
19INR0035 | Norton Solar | SS Completed, FIS Started, No IA | 8minutenergy | tap 138kV 6325 Chad to 6340 Balg, 10mi from Chad | Runnels | WEST | 2019-12-01 | SOL | PV | 125 |  | 2017-03-06 | 2017-04-20 | 2017-11-08 |  |  | No | Not Required | Not Required | Not Required
19INR0036 | Oxbow Solar | SS Completed, FIS Started, No IA | BNB Renewables | 59905 Faraday 345kV | Borden | WEST | 2020-12-15 | SOL | PV | 225 |  | 2017-02-28 | 2017-04-13 | 2017-10-10 |  |  | No | Not Required | Not Required | Not Required
19INR0038 | High Lonesome W | SS Completed, FIS Started, IA | Swift Current Energy | tap 345kV 76002 Bakersfield - 76005 Schneeman | Crockett | WEST | 2019-11-30 | WIN | WT | 449.5 |  | 2017-03-10 | 2017-04-17 | 2017-07-18 |  | 2018-04-17 | Yes | Not Required | Not Required | Not Required
19INR0041 | Myrtle Solar | SS Completed, FIS Started, No IA | Sunchase Power | 42110 Angleton 138kv or line tap to Rosharon 44600 | Brazoria | COASTAL | 2020-05-01 | SOL | PV | 240 |  | 2017-03-15 | 2017-04-28 | 2017-05-09 |  |  | No | Not Required | Not Required | Not Required
19INR0042 | Long Point Solar | SS Completed, FIS Started, No IA | SunChase Power | tap 138kV 44010 WAP - 42981 Nash98 | Brazoria | COASTAL | 2020-09-01 | SOL | PV | 100 |  | 2017-03-15 | 2017-04-20 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
19INR0044 | Lily Solar | SS Completed, FIS Completed, No IA | SunChase Power | tap 138kV 6904 CombinRC - 6908 ScuryRC | Kaufman | NORTH | 2020-12-01 | SOL | PV | 150 |  | 2017-03-28 | 2017-04-28 | 2017-05-30 | 2018-09-26 |  | No | Not Required | Not Required | Not Required
19INR0045 | Rayos Del Sol | SS Completed, FIS Completed, IA | Tradewind Energy | tap 138kV 8554 Mesquite - 80103 Rangerville | Cameron | COASTAL | 2020-12-31 | SOL | PV | 150 |  | 2017-03-28 | 2017-05-22 | 2017-03-28 | 2018-06-13 | 2018-11-06 | No | Not Required | Not Required | Not Required
19INR0048 | Buenos Aires 1 W | SS Completed, FIS Started, No IA | Terra-Gen | tap 138kV 8380 NEdinb - 8896 Rachal | Hidalgo | SOUTH | 2019-12-31 | WIN | WT | 200 |  | 2017-03-30 | 2017-05-03 | 2017-08-28 |  |  | No | Not Required | Not Required | Not Required
19INR0049 | Buenos Aires 2 W | SS Completed, FIS Started, No IA | Terra-Gen | tap 345kV 8905 N Edinb - 8455 Lon Hill | Hidalgo | SOUTH | 2019-12-31 | WIN | WT | 200 |  | 2017-03-30 | 2017-05-03 | 2017-08-28 |  |  | No | Not Required | Not Required | Not Required
19INR0051 | Vera Wind | SS Completed, FIS Started, IA | Longroad Energy | tap 345kV 60500 EdithC - 60700 Gauss | Knox | WEST | 2020-06-01 | WIN | WT | 242.8 | COD | 2017-04-04 | 2017-05-18 | 2017-06-13 |  | 2018-07-10 | No | Not Required | Not Required | Not Required
19INR0052 | TG East Wind | SS Completed, FIS Started, IA | Northrenew | new 345kV sub Coulomb in 60500 EdithC - 60700 Gauss line | Knox | WEST | 2019-12-15 | WIN | WT | 275.6 |  | 2017-04-04 | 2017-05-18 | 2017-06-13 |  | 2018-10-22 | No | Not Required | Not Required | Not Required
19INR0053 | Hidalgo II Wind | SS Completed, FIS Started, No IA | EDP Renewables | 161705 Mirasole 345kV | Hidalgo | SOUTH | 2019-10-31 | WIN | WT | 51 |  | 2017-04-05 | 2017-05-19 | 2017-07-12 |  |  | No | Not Required | Not Required | Not Required
19INR0054 | Monte Cristo 1 W | SS Completed, FIS Started, No IA | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | SOUTH | 2019-12-31 | WIN | WT | 200 |  | 2017-04-11 | 2017-05-03 | 2017-07-28 |  |  | No | Not Required | Not Required | Not Required
19INR0055 | Monte Cristo II W | SS Completed, FIS Started, No IA | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | SOUTH | 2019-12-31 | WIN | WT | 200 |  | 2017-04-11 | 2017-05-03 | 2017-07-28 |  |  | No | Not Required | Not Required | Not Required
19INR0056 | Chamon 2 | SS Completed, FIS Completed, No IA | Castleman Power | 40260 Chamon 138kV | Harris | HOUSTON | 2020-05-01 | GAS | GT | 100 |  | 2017-04-24 | 2017-06-09 | 2017-07-06 | 2018-05-07 |  | No
19INR0057 | Old Bloomington Road | SS Completed, FIS Started, No IA | Castleman Power | 8143 Dupont 138kV | Victoria | SOUTH | 2019-06-01 | GAS | GT | 100 |  | 2017-04-18 | 2017-05-22 | 2017-11-29 |  |  | No | Not Required | Not Required
19INR0070 | Trevino Solar | SS Completed, FIS Started, No IA | S Power | 78015 Rosita 138kV | Maverick | SOUTH | 2020-12-15 | SOL | PV | 216 |  | 2017-04-19 | 2017-06-02 | 2017-11-30 |  |  | No | Not Required | Not Required | Not Required
19INR0073 | Shakes Solar | SS Completed, FIS Started, IA | Cypress Creek Renewables | 8283 Asherton 138kV | Zavala | SOUTH | 2019-12-31 | SOL | PV | 206 |  | 2017-05-03 | 2017-06-15 | 2017-05-03 |  | 2018-10-26 | No | Not Required | Not Required | Not Required
19INR0074 | Karankawa 2 Wind | SS Completed, FIS Started, IA | Avangrid | tap 345kV 8455 Lon Hill - 5725 Pawnee | San Patricio | COASTAL | 2019-12-31 | WIN | WT | 200 |  | 2017-05-12 | 2017-06-23 | 2017-10-04 |  | 2018-03-02 | Yes | Not Required | Not Required | Not Required | 2018-03-02 |  | 2018-03-02
19INR0075 | Horseshoe Bend Solar | SS Completed, FIS Started, No IA | Clenera | 1444 Brown 345kV | Coleman | WEST | 2020-12-31 | SOL | PV | 300 |  | 2017-06-23 | 2017-08-07 | 2018-02-09 |  |  | No | Not Required | Not Required | Not Required
19INR0080 | Whitehorse Wind | SS Completed, FIS Started, IA | Clearway Energy | 68001 Clayton 345kV | Fisher | WEST | 2019-12-15 | WIN | WT | 418.9 | MW Size COD | 2017-06-23 | 2017-08-07 | 2018-02-16 |  | 2018-12-05 | Yes | Not Required | Not Required | Not Required
19INR0081 | Anson Solar | SS Completed, FIS Started, No IA | Coronal Energy | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2020-06-30 | SOL | PV | 600 |  | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  | No | Not Required | Not Required | Not Required
19INR0083 | Oberon Solar | SS Completed, FIS Completed, IA | 174 Power Global | tap 138kV 1292 Ectorharp - 1013 Wolf | Ector | WEST | 2019-12-15 | SOL | PV | 180 |  | 2017-05-31 | 2017-07-13 | 2017-05-31 | 2018-05-18 | 2018-10-11 | Yes | Not Required | Not Required | Not Required
19INR0085 | Blue Jay Solar | SS Completed, FIS Started, No IA | Open Road Renewables | 4 Iola 138kV | Grimes | NORTH | 2019-12-15 | SOL | PV | 210 |  | 2017-05-30 | 2017-08-11 | 2018-02-15 |  |  | No | Not Required | Not Required | Not Required
19INR0088 | Aragorn Solar | SS Completed, FIS Started, IA | Intersect Power | tap 138kV 71097 LCulberson - 7387 Kunitz | Culberson | WEST | 2020-07-31 | SOL | PV | 186.3 |  | 2017-05-30 | 2017-07-21 | 2017-08-08 |  | 2018-05-31 | No | Not Required | Not Required | Not Required
19INR0091 | Phoenix Solar | SS Completed, FIS Started, No IA | Alpin Sun | 1808 Bonham 138kV | Fannin | NORTH | 2020-03-01 | SOL | PV | 82.3 |  | 2017-06-23 | 2017-08-23 | 2017-08-09 |  |  | No | Not Required | Not Required | Not Required
19INR0092 | Prospero Solar | SS Completed, FIS Completed, IA | Longroad Energy | 79650 Clearfork 345kV + 10 mile gen-tie | Andrews | WEST | 2020-06-01 | SOL | PV | 300 | COD | 2017-06-23 | 2017-08-07 | 2017-07-11 | 2018-08-10 | 2018-04-20 | No | Not Required | Not Required | Not Required
19INR0093 | Solemio | SS Completed, FIS Started, No IA | Alpin Sun | tap 138kV 1698 Sulphur Springs - 1814 Sulspg | Hopkins | NORTH | 2020-05-31 | SOL | PV | 79.8 |  | 2017-06-23 | 2017-08-23 | 2017-08-09 |  |  | No | Not Required | Not Required | Not Required
19INR0096 | Shamrock Wind | SS Completed, FIS Started, No IA | Eon | 76005 Schneeman Draw 345kV | Crockett | WEST | 2020-12-31 | WIN | WT | 201.6 |  | 2017-07-28 | 2017-09-13 | 2017-10-04 |  |  | No | Not Required | Not Required | Not Required
19INR0097 | Shamrock Wind II | SS Completed, FIS Started, No IA | Eon | 76005 Schneeman Draw 345kV | Crockett | WEST | 2020-12-15 | WIN | WT | 201.6 |  | 2017-07-28 | 2017-09-13 | 2017-10-02 |  |  | No | Not Required | Not Required | Not Required
19INR0098 | Pease River Wind | SS Completed, FIS Started, No IA | Eon | 60500 Edith Clarke 345kV | Hardeman | WEST | 2019-12-31 | WIN | WT | 301.4 |  | 2017-07-11 | 2017-08-28 | 2017-07-14 |  |  | No | Not Required | Not Required | Not Required
19INR0099a | Kontiki 1 Wind (ERIK) | SS Completed, FIS Started, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2020-06-30 | WIN | WT | 255.3 | COD | 2017-06-22 | 2017-08-04 | 2017-09-28 |  | 2018-05-07 | Yes | Not Required | Not Required | Not Required | 2018-05-07 |  | 2018-05-07
19INR0099b | Kontiki 2 Wind (ERNEST) | SS Completed, FIS Started, IA | CIP | 59903 Bearkat 345kV | Glasscock | WEST | 2021-06-30 | WIN | WT | 255.3 | Proj Name COD | 2017-06-22 | 2017-08-04 | 2017-09-28 |  | 2018-05-07 | Yes | Not Required | Not Required | Not Required | 2018-05-07 |  | 2018-05-07
19INR0100 | Prairie Hill Wind | SS Completed, FIS Completed, IA | Prairie Hill LLC | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | McLennan | NORTH | 2020-06-01 | WIN | WT | 300 |  | 2017-06-19 | 2017-08-11 | 2017-06-19 | 2018-05-18 | 2018-09-17 | Yes | Not Required | Not Required | Not Required
19INR0101 | Tehuacana Wind | SS Completed, FIS Started, No IA | Infinity Renewables | 46020 Limestone 345kV + 34mi gentie | Limestone | NORTH | 2019-12-01 | WIN | WT | 600 |  | 2017-06-19 | 2017-08-11 | 2017-06-19 |  |  | No | Not Required | Not Required | Not Required
19INR0102 | Queen Solar | SS Completed, FIS Started, IA | Cielo | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | WEST | 2019-11-30 | SOL | PV | 400 |  | 2017-07-11 | 2017-08-28 | 2018-02-26 |  | 2018-09-27 | No | Not Required | Not Required | Not Required
19INR0103 | Rodeo Solar | SS Completed, FIS Started, No IA | Core Solar | tap 138kV 1134 Littman - 1135 Gasland | Andrews | WEST | 2019-12-31 | SOL | PV | 205 |  | 2017-06-29 | 2017-08-04 | 2018-02-19 |  |  | No | Not Required | Not Required | Not Required
19INR0110 | Angelina Solar | SS Completed, FIS Started, No IA | EDP Renewables | 3349 TMPLinla 138kV | Angelina | NORTH | 2021-10-31 | SOL | PV | 150 |  | 2017-07-26 | 2017-09-15 | 2018-03-15 |  |  | No | Not Required | Not Required | Not Required
19INR0111 | Tom Green Solar | SS Completed, FIS Started, No IA | EDP Renewables | tap 138kV 6480 SAPS - 60423 Treadwell | Tom Green | WEST | 2021-10-31 | SOL | PV | 150 |  | 2017-07-26 | 2017-09-13 | 2018-03-15 |  |  | No | Not Required | Not Required | Not Required
19INR0112 | Cranel Wind | SS Completed, FIS Completed, IA | Eon | tap 345kV 8164 Coleto - 8455 Lon Hill | Refugio | COASTAL | 2019-12-31 | WIN | WT | 220 |  | 2017-09-12 | 2017-11-01 | 2017-11-30 | 2018-08-30 | 2018-10-12 | Yes | Not Required | Not Required | Not Required | 2018-10-12 |  | 2018-10-12
19INR0113 | County Line Solar | SS Completed, FIS Started, No IA | S Power | 60385 Solstice 138kV, Tap between Pigcreek (60393) and TNFLATTOP (38069) | Pecos | WEST | 2020-12-15 | SOL | PV | 250 |  | 2017-08-15 | 2017-11-01 | 2017-08-15 |  |  | No | Not Required | Not Required | Not Required
19INR0114 | Rambler Solar | SS Completed, FIS Started, IA | Recurrent Energy | 76009 Twin Buttes 345kV | Tom Green | WEST | 2019-12-30 | SOL | PV | 150 |  | 2017-08-09 | 2017-10-10 | 2018-01-05 |  | 2018-10-11 | No | Not Required | Not Required | Not Required
19INR0115 | Blackwater Draw Solar | SS Completed, FIS Started, No IA | Core Solar | tap 138kV 1170 Paul Davis tap - 18880 Jim Payne | Dawson | WEST | 2020-12-31 | SOL | PV | 151.9 |  | 2017-07-28 | 2017-10-09 | 2018-04-12 |  |  | No | Not Required | Not Required | Not Required
19INR0117 | Road Runner Crossing Wind 1 | SS Completed, FIS Started, No IA | Eon | tap 345kV 68005 WShack - 68050 Romney | Eastland | NORTH | 2020-12-31 | WIN | WT | 200.2 |  | 2017-09-08 | 2017-11-07 | 2018-03-05 |  |  | No | Not Required | Not Required | Not Required
19INR0120 | Sherbino II Wind repower | SS Completed, FIS Completed, No IA | BP | 131454 Keo_3 138kV | Pecos | WEST | 2020-03-01 | WIN | WT | -13 |  | 2017-08-18 | 2017-09-28 | 2017-09-21 | 2018-12-04 |  | No | Not Required | Not Required | Not Required
19INR0121 | Galloway Solar | SS Completed, FIS Started, No IA | 8minutenergy | tap 345kV 6444 RedCr - 76006 Bow or tap 345kV 76009 Twin - 1444 Brown | Concho | WEST | 2020-12-01 | SOL | PV | 360 |  | 2017-08-25 | 2017-10-02 | 2017-08-25 |  |  | No | Not Required | Not Required | Not Required
19INR0123 | GSE Eleven | SS Completed, FIS Started, No IA | Alpin Sun | tap 138kV 3175 Canton - 3173 Expmtr | Van Zandt | NORTH | 2020-11-01 | SOL | PV | 135 | COD | 2017-09-12 | 2017-11-13 | 2017-12-05 |  |  | No | Not Required | Not Required | Not Required
19INR0128 | White Mesa Wind | SS Completed, FIS Started, IA | Apex Clean | 76005 Schneeman Draw 345kV | Crockett | WEST | 2019-12-23 | WIN | WT | 500 |  | 2017-09-08 | 2017-11-20 | 2018-01-29 |  | 2018-12-19 | No | Not Required | Not Required | Not Required
19INR0129 | Flatland Solar | SS Completed, FIS Started, No IA | Sunfinity Renewables | 1309 Bluftap 138kV or tap 138kV 1032 Morgan - 1064 Sun | Scurry | WEST | 2020-07-15 | SOL | PV | 147 |  | 2017-10-20 | 2017-12-13 | 2018-06-13 |  |  | No | Not Required | Not Required | Not Required
19INR0131 | Cutlass Solar | SS Completed, FIS Started, No IA | Lendlease Energy | tap 345kV 44000 WAP - 44200 Hillje, probably | Fort Bend | HOUSTON | 2020-06-01 | SOL | PV | 300 |  | 2017-09-21 | 2017-11-20 | 2018-05-15 |  |  | No | Not Required | Not Required | Not Required
19INR0132 | Los Porciones I | SS Completed, FIS Started, No IA | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | SOUTH | 2019-12-31 | WIN | WT | 200 |  | 2017-09-22 | 2017-11-13 | 2017-09-22 |  |  | No | Not Required | Not Required | Not Required
19INR0133 | Los Porciones II | SS Completed, FIS Started, No IA | Terra-Gen | 8574 Pomelo 345kV | Hidalgo | SOUTH | 2019-12-31 | WIN | WT | 200 |  | 2017-09-22 | 2017-11-13 | 2017-09-22 |  |  | No | Not Required | Not Required | Not Required
19INR0134 | Cottonwood Bayou | SS Completed, FIS Started, No IA | Sunchase Power | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2020-11-30 | SOL | PV | 150 |  | 2017-09-22 | 2017-11-17 | 2018-02-15 |  |  | No | Not Required | Not Required | Not Required
19INR0135 | Hill Solar | SS Completed, FIS Started, No IA | Sunchase Power | tap 69kV 3523 Hillsboro - 3532 Itasco | Hill | NORTH | 2020-10-01 | SOL | PV | 80 |  | 2017-09-22 | 2017-11-17 | 2018-05-10 |  |  | No | Not Required | Not Required | Not Required
19INR0136 | Able Solar | SS Completed, FIS Started, No IA | Sunchase Power | 12469 Able Spring 138kV | Kaufman | NORTH | 2020-10-01 | SOL | PV | 50 |  | 2017-09-22 | 2017-11-17 | 2018-05-10 |  |  | No | Not Required | Not Required | Not Required
19INR0138 | Buffalo Gap 4 | SS Completed, FIS Started, No IA | AES | 66216 Bluff Creek 138kV | Nolan | WEST | 2020-09-01 | WIN | WT | 175 |  | 2017-10-06 | 2017-11-20 | 2017-10-06 |  |  | No | Not Required | Not Required | Not Required
19INR0142 | Bacon Switch Solar | SS Completed, FIS Started, No IA | SunChase Power | tap 345kV 6101 Riley - 1425 Fisher | Wichita | WEST | 2020-05-31 | SOL | PV | 150 |  | 2017-10-11 | 2017-11-08 | 2018-02-15 |  |  | No | Not Required | Not Required | Not Required
19INR0144 | Bird Dog Wind | SS Completed, FIS Started, No IA | Americlean | 1301 Willow Valley 138kV | Borden | WEST | 2019-10-01 | WIN | WT | 300 |  | 2017-10-20 | 2017-12-14 | 2018-07-05 |  |  | No | Not Required | Not Required | Not Required
19INR0145 | Aquilla Lake | SS Completed, FIS Started, No IA | Nextera | 68090 Sam Switch 345 kV | Hill | NORTH | 2020-08-30 | WIN | WT | 202 |  | 2018-07-18 | 2018-09-20 | 2018-07-18 |  |  | No | Not Required | Not Required | Not Required
19INR0147 | March Road Solar | SS Completed, FIS Started, No IA | Eon | tap 345kV 76009 TwinB - 1444 Brown | Tom Green | WEST | 2020-12-30 | SOL | PV | 200 | COD | 2017-11-13 | 2018-01-08 | 2017-12-01 |  |  | No | Not Required | Not Required | Not Required
19INR0149 | Lapetus Solar | SS Completed, FIS Completed, No IA | 7x Energy | 1284 Shafter Lake 138kV | Andrews | WEST | 2019-11-30 | SOL | PV | 50 |  | 2018-02-22 | 2018-02-26 | 2017-12-05 | 2018-08-30 |  | No | Not Required | Not Required | Not Required
19INR0150 | Millhouse Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 69kV 8500 Alice - 8889 Stadium | Jim Wells | SOUTH | 2019-12-31 | SOL | PV | 75 |  | 2017-11-13 | 2018-02-23 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
19INR0151 | Impact Solar | SS Completed, FIS Started, No IA | Alpin Sun | tap 345kV 1695 Moses - 1692 Paris | Lamar | NORTH | 2020-11-01 | SOL | PV | 197 |  | 2017-12-18 | 2018-02-01 | 2018-05-04 |  |  | No | Not Required | Not Required | Not Required
19INR0155 | Morrow Lake Solar | SS Completed, FIS Started, No IA | Sunchase Power | tap 138kV 5895 Pearsall - 5700 Miracle | Frio | SOUTH | 2020-10-01 | SOL | PV | 150 |  | 2017-12-05 | 2018-01-15 | 2018-02-15 |  |  | No | Not Required | Not Required | Not Required
19INR0156 | Grape Creek Wind | SS Completed, FIS Started, No IA | Apex Clean | tap 345kV 76009 TwinB - 76090 Divide | Coke | WEST | 2019-12-23 | WIN | WT | 524.4 |  | 2017-12-06 | 2018-02-23 | 2018-01-25 |  |  | No | Not Required | Not Required | Not Required
19INR0159 | Reiher Solar | SS Completed, FIS Started, No IA | Energie Kontor | 76597 Robb Sw 138kV | Upton | WEST | 2020-12-31 | SOL | PV | 101.6 |  | 2018-01-29 | 2018-03-27 | 2018-08-14 |  |  | No | Not Required | Not Required | Not Required
19INR0160 | Great Dane Wind | SS Completed, FIS Started, No IA | Seventus | 5546 Danevang 138kV | Wharton | SOUTH | 2020-03-01 | WIN | WT | 302.5 |  | 2018-01-03 | 2018-02-15 | 2018-01-03 |  |  | No | Not Required | Not Required | Not Required
19INR0161 | Pierce Wind | SS Completed, FIS Started, No IA | Seventus | 345kV ROW between Hillje & WAP or 345kV Bailey to Hillje | Wharton | SOUTH | 2020-03-01 | WIN | WT | 300 |  | 2018-01-03 | 2018-02-16 | 2018-01-03 |  |  | No | Not Required | Not Required | Not Required
19INR0163 | Sage Draw Wind | SS Completed, FIS Started, IA | Lincoln Clean | 79641 Farmland 345kV | Lynn | WEST | 2019-10-31 | WIN | WT | 300 |  | 2016-03-14 | 2016-03-23 | 2016-04-22 |  | 2018-01-03 | No | Not Required | Not Required | Not Required
19INR0165 | Barranca Wind | SS Completed, FIS Started, No IA | Enerverse | tap 345kV 80307 Delsol - 80380 Cabezon | Zapata | SOUTH | 2020-04-30 | WIN | WT | 201.6 |  | 2018-05-09 | 2018-05-25 | 2018-02-28 |  |  | No | Not Required | Not Required | Not Required
19INR0166 | Loma Pinta II | SS Completed, FIS Started, No IA | Enerverse | 5705 Fowlerton 138kV | La Salle | SOUTH | 2019-12-31 | WIN | WT | 201.6 |  | 2018-02-28 | 2018-04-16 | 2018-02-28 |  |  | No | Not Required | Not Required | Not Required
19INR0167 | Gold Creek Solar | SS Completed, FIS Started, No IA | S Power | 1163 Lamesa 138kV | Dawson | WEST | 2020-12-15 | SOL | PV | 140 |  | 2018-05-04 | 2018-06-28 | 2018-05-04 |  |  | No | Not Required | Not Required | Not Required
19INR0169 | Sun Valley | SS Completed, FIS Started, No IA | Alpin Sun | tap 345kV 68090 Sam Sw - 3405 or 13405 Tradinghouse | Hill | NORTH | 2020-12-01 | SOL | PV | 135 |  | 2018-03-02 | 2018-04-17 | 2018-07-19 |  |  | No | Not Required | Not Required | Not Required
19INR0171 | Concho Valley Solar | SS Completed, FIS Started, No IA | Merit SI | tap 138kV 6480 SAPOWER - 6490 Santiago | Tom Green | WEST | 2020-11-01 | SOL | PV | 150 |  | 2018-03-02 | 2018-04-13 | 2018-03-02 |  |  | No | Not Required | Not Required | Not Required
19INR0172 | Dillon Gulch | SS Completed, FIS Started, No IA | AES | tap 345kV 11420 Sweetwater East Switch - 11406 Central Bluff Switch | Nolan | WEST | 2020-03-31 | WIN | WT | 175 |  | 2018-04-12 | 2018-06-13 | 2018-04-12 |  |  | No | Not Required | Not Required | Not Required
19INR0173 | Magnet Wind | SS Completed, FIS Started, No IA | Seventus | 43190 South Lane City 138kV | Wharton | SOUTH | 2020-06-30 | WIN | WT | 125 |  | 2018-04-13 | 2018-06-12 | 2018-04-13 |  |  | No | Not Required | Not Required | Not Required
19INR0174 | Elbow Creek repower | SS Completed, FIS Completed, No IA | NRG | 1058 Longshore 345kV | Howard | WEST | 2019-09-01 | WIN | WT | 0 |  | 2018-05-04 | 2018-05-18 | 2018-07-19 | 2018-09-17 |  | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 11:56 | 2018-10-31
19INR0175 | Changing Winds | SS Completed, FIS Started, No IA | Triglobal | 79501 Ogallala 345kV | Castro | PANHANDLE | 2020-10-30 | WIN | WT | 289 | FIS Request MW Size COD | 2018-04-26 | 2018-06-12 |  |  |  | No | Not Required | Not Required | Not Required
19INR0176 | Roughneck Storage | SS Completed, FIS Started, No IA | Glidepath | 43390 W Columbia 69kV | Brazoria | COASTAL | 2020-04-01 | OTH | BA | 52.25 | Proj Name MW Size | 2018-05-09 | 2018-07-13 |  |  |  | No | Not Required | Not Required | Not Required
19INR0177 | Shanghai Wind | SS Completed, FIS Started, No IA | Seventus | 8104 Lane City PM 138kV | Wharton | SOUTH | 2019-12-31 | WIN | WT | 153.3 |  | 2018-05-09 | 2018-06-21 | 2018-05-09 |  |  | No | Not Required | Not Required | Not Required
19INR0179 | Barranca Wind II | SS Completed, FIS Started, No IA | Enerverse | tap 345kV 80307 Delsol - 80380 Cabezon | Zapata | SOUTH | 2020-04-30 | WIN | WT | 201.6 |  | 2018-05-15 | 2018-06-01 | 2018-05-15 |  |  | No | Not Required | Not Required | Not Required
19INR0180 | Friendswood II | SS Completed, FIS Started, No IA | Quantum | 47170 HOC 138kV | Brazoria | COASTAL | 2019-11-15 | GAS | GT | 117 |  | 2018-05-17 | 2018-07-11 | 2018-05-17 |  |  | No
19INR0182 | Blue Summit Wind III | SS Completed, FIS Started, No IA | Nextera | 61001 Jim Treece 345kV | Wilbarger | WEST | 2019-05-31 | WIN | WT | 200 |  | 2018-06-06 | 2018-07-24 | 2018-06-06 |  |  | No | Not Required | Not Required | Not Required
19INR0184 | Oxy Solar | SS Completed, FIS Started, No IA | Oxy Renewable Energy | 11256 Goldsmith 138kV | Ector | WEST | 2019-07-15 | SOL | PV | 16.2 |  | 2018-07-18 | 2018-09-20 | 2018-08-07 |  |  | No | Not Required | Not Required | Not Required
19INR0185 | Lapetus Solar 2 | SS Completed, FIS Started, No IA | 7x Energy | 1284 Shafter Lake 138kV | Andrews | WEST | 2019-12-15 | SOL | PV | 100 |  | 2018-07-26 | 2018-07-26 | 2018-07-26 |  |  | No | Not Required | Not Required | Not Required
19INR0187 | John Paul Jones | SS Completed, FIS Started, No IA | Dflex Power | 46510 Tomball 138kV | Harris | HOUSTON | 2020-05-31 | GAS | GT | 18.6 |  | 2018-08-02 | 2018-09-28 | 2018-08-02 |  |  | No | Not Required | Not Required
19INR0188 | Millhouse Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 69kV 8500 Alice - 8889 Stadium | Jim Wells | SOUTH | 2019-12-31 | OTH | BA | 38 |  | 2017-11-13 | 2018-02-23 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
20INR0005 | Shorthorn 2 Solar | SS Completed, FIS Started, No IA | 8minutenergy | 60501 Tesla 345kV | Childress | PANHANDLE | 2020-10-01 | SOL | PV | 200 |  | 2016-10-26 | 2016-11-14 | 2016-12-13 |  |  | No | Not Required | Not Required | Not Required
20INR0011 | Ranchero Wind | SS Completed, FIS Completed, IA | Scout Clean Energy | 345kV Bus#: 7053 Noelke | Crockett | WEST | 2019-06-04 | WIN | WT | 300 |  | 2017-06-23 | 2017-08-07 | 2017-07-03 | 2018-11-01 | 2018-05-02 | Yes | Not Required | Not Required | Not Required | 2018-08-03 | 2018-10-31 | 2018-08-03
20INR0012 | Lueders Solar | SS Completed, FIS Started, No IA | Innovative Solar | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | WEST | 2020-08-01 | SOL | PV | 40 |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0013 | Basalt Solar | SS Completed, FIS Started, No IA | Innovative Solar | tap 138kV 8234 Uvalde - 8241 Razorback | Uvalde | SOUTH | 2020-08-01 | SOL | PV | 20 |  | 2017-07-11 | 2017-09-01 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0014 | Obsidian Solar | SS Completed, FIS Started, No IA | Innovative Solar | 6131 Padr 69kV | Cottle | WEST | 2020-08-01 | SOL | PV | 60 |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0015 | Citrine Solar | SS Completed, FIS Started, No IA | Innovative Solar | Tap 138kV 6135 Paducah Clare - 6117 E Munday | Cottle | WEST | 2020-08-01 | SOL | PV | 45 |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0016 | Opal Solar | SS Completed, FIS Started, No IA | Innovative Solar | tap 345kV 60501 Tesla - 60500 Edith Clark | Hardeman | WEST | 2020-08-01 | SOL | PV | 45 |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  |  | No | Not Required | Not Required | Not Required
20INR0019 | Trinity Hills Wind repower | SS Completed, FIS Completed, IA | BP | 150751 & 150752 Trinity Hills 34.5kV | Young | WEST | 2020-11-01 | WIN | WT | -27 |  | 2017-07-20 | 2017-09-08 | 2017-09-21 | 2018-08-02 | 2018-10-17 | No | Not Required | Not Required | Not Required
20INR0021 | Garnet Solar | SS Completed, FIS Completed, No IA | Innovative Solar | tap 69kV 3648 Granger - 3649 Taylor | Williamson | SOUTH | 2020-07-01 | SOL | PV | 20 |  | 2017-08-10 | 2017-10-10 | 2017-10-20 | 2018-09-28 |  | No | Not Required | Not Required | Not Required
20INR0022 | Sandine Solar | SS Completed, FIS Started, No IA | Innovative Solar | tap 138kV 6135 Paducah - 6320 Tardis | Cottle | WEST | 2020-08-01 | SOL | PV | 30 |  | 2017-08-10 | 2017-10-22 | 2017-10-24 |  |  | No | Not Required | Not Required | Not Required
20INR0023 | Agate Solar | SS Completed, FIS Completed, No IA | Innovative Solar | new 345kV sub Forbes in 68090 Sam - 1906 Venus S or -1907 Venus N | Ellis | NORTH | 2020-08-01 | SOL | PV | 60 |  | 2017-08-10 | 2017-10-18 | 2017-10-23 | 2018-10-26 |  | No | Not Required | Not Required | Not Required
20INR0024 | Fluorite Solar | SS Completed, FIS Completed, No IA | Innovative Solar | 5817 FerrisSw 69kV | Uvalde | SOUTH | 2020-08-01 | SOL | PV | 25 |  | 2017-08-10 | 2017-10-22 | 2017-10-20 | 2018-11-02 |  | No | Not Required | Not Required | Not Required
20INR0025 | Spinel Solar | SS Completed, FIS Completed, No IA | Innovative Solar | tap 138kV 5225 Hondo - 5813 Pearson | Medina | SOUTH | 2020-08-01 | SOL | PV | 30 |  | 2017-08-10 | 2017-10-09 | 2017-10-20 | 2018-07-26 |  | No | Not Required | Not Required | Not Required
20INR0026 | Longbow Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 42870 Liverpool 138kV | Brazoria | COASTAL | 2020-03-01 | SOL | PV | 70 |  | 2017-08-16 | 2017-10-13 | 2017-08-16 |  |  | No | Not Required | Not Required | Not Required
20INR0029 | JA Ranch | SS Completed, FIS Started, No IA | EDF Renewable Energy | tap 345kV 6101 Riley - 1730 W Krum | Clay | WEST | 2020-12-01 | WIN | WT | 242 |  | 2017-09-12 | 2017-11-07 | 2018-05-08 |  |  | No | Not Required | Not Required | Not Required
20INR0031 | Rippey Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 138kV 1988 ValleyV - 1710 Gainvl | Cooke | NORTH | 2020-03-01 | SOL | PV | 60 |  | 2017-10-02 | 2017-11-13 | 2018-02-06 |  |  | No | Not Required | Not Required | Not Required
20INR0032 | IP Titan | SS Completed, FIS Started, No IA | Intersect Power | 71097 LCRA Culberson 138kV | Culberson | WEST | 2021-06-30 | SOL | PV | 272 |  | 2017-10-12 | 2017-12-08 | 2018-01-19 |  |  | No | Not Required | Not Required | Not Required
20INR0033 | Cooke Wind II | SS Completed, FIS Started, No IA | EDP Renewables | tap 345kV 1730 KrumW - 2373 Anna | Cooke | NORTH | 2020-10-31 | WIN | WT | 152 |  | 2017-10-18 | 2017-12-11 | 2018-06-14 |  |  | No | Not Required | Not Required | Not Required
20INR0035 | Angus Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 177 Bosque - 181 Cayote | Bosque | NORTH | 2020-08-31 | SOL | PV | 113 |  | 2017-11-13 | 2018-01-02 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
20INR0036 | Stillwater Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 345kV 8905 N Edinb - 8455 Lon Hill | Nueces | COASTAL | 2020-08-31 | SOL | PV | 144 |  | 2017-11-13 | 2018-01-15 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
20INR0037 | Coniglio Solar | SS Completed, FIS Started, No IA | Belltown Power | 1809 Boistret 138kV | Fannin | NORTH | 2020-03-01 | SOL | PV | 135 |  | 2017-11-28 | 2018-01-23 | 2018-05-25 |  |  | No | Not Required | Not Required | Not Required
20INR0038 | Red Mud Creek | SS Completed, FIS Started, No IA | Eon | tap 345kV 11318 Scurry - 59905 Faraday or 11318-59900 Long Draw | Borden | WEST | 2020-12-31 | WIN | WT | 201 |  | 2017-11-29 | 2018-02-05 | 2018-03-15 |  |  | No | Not Required | Not Required | Not Required
20INR0039 | Red Mud Creek II | SS Completed, FIS Started, No IA | Eon | tap 345kV 11318 Scurry - 59905 Faraday or 11318-59900 Long Draw | Borden | WEST | 2021-12-31 | WIN | WT | 102 |  | 2017-11-29 | 2018-02-05 | 2018-07-03 |  |  | No | Not Required | Not Required | Not Required
20INR0040 | Montgomery Ranch Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 60500 EdithC - 60700 Gauss | Foard | WEST | 2021-12-15 | WIN | WT | 200.2 |  | 2017-12-18 | 2018-02-06 | 2018-06-20 |  |  | No | Not Required | Not Required | Not Required
20INR0042 | Chalupa Wind | SS Completed, FIS Started, IA | Acciona | Rio Hondo- La Palma 138kV | Cameron | COASTAL | 2020-12-21 | WIN | WT | 174 |  | 2017-12-22 | 2018-02-06 | 2018-01-24 |  | 2018-09-28 | Yes | Not Required | Not Required | Not Required | 2018-10-18 |  | 2018-10-18
20INR0043 | Gulf Wind 2 | SS Completed, FIS Started, No IA | Pattern Energy | 80071 Zorillo 345kV | Kenedy | COASTAL | 2020-05-01 | WIN | WT | 180 |  | 2018-01-04 | 2018-02-20 | 2018-02-14 |  |  | No | Not Required | Not Required | Not Required
20INR0044 | French Goldston Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 138kV 1431 Graham - 1477 Rice OR 1596 Graham 138kV | Young | WEST | 2020-06-01 | SOL | PV | 120 |  | 2018-01-03 | 2018-03-12 |  |  |  | No | Not Required | Not Required | Not Required
20INR0045 | Maverick Creek I | SS Completed, FIS Started, IA | RES Americas | tap 345kV 6444 RedCr - 76006 Bow or tap 345kV 76009 Twin - 1444 Brown | Concho | WEST | 2020-09-01 | WIN | WT | 268.5 | MW Size | 2018-01-05 | 2018-02-20 | 2018-03-05 |  | 2018-07-31 | No | Not Required | Not Required | Not Required
20INR0046 | Maverick Creek II | SS Completed, FIS Started, IA | RES Americas | tap 345kV 6444 RedCr - 76006 Bow or tap 345kV 76009 Twin - 1444 Brown | Concho | WEST | 2020-09-01 | WIN | WT | 255.9 | MW Size | 2018-01-05 | 2018-02-20 | 2018-03-05 |  | 2018-07-31 | No | Not Required | Not Required | Not Required
20INR0048 | Century Oak Wind | SS Completed, FIS Started, No IA | Engie | tap 138kV 6670 Putnam - 6317 Cisco | Callahan | WEST | 2020-12-01 | WIN | WT | 126 |  | 2018-01-29 | 2018-02-28 | 2018-05-17 |  |  | No | Not Required | Not Required | Not Required
20INR0050 | Castro Solar | SS Completed, FIS Started, No IA | Oaktree Development | 79501 Ogallala 345kV | Castro | PANHANDLE | 2020-01-01 | SOL | PV | 200 |  | 2018-02-08 | 2018-04-09 | 2018-05-15 |  |  | No | Not Required | Not Required | Not Required
20INR0052 | Griffin Trail Wind | SS Completed, FIS Started, No IA | Innergex | tap 345kV 60500 EdithC - 60702 Gauss | Knox | WEST | 2020-09-30 | WIN | WT | 201.6 |  | 2018-03-05 | 2018-05-04 |  |  |  | No | Not Required | Not Required | Not Required
20INR0053 | Bravepost Solar | SS Completed, FIS Started, No IA | Recurrent Energy | 6444 Red Creek 345kV | Tom Green | WEST | 2020-12-31 | SOL | PV | 200 |  | 2018-02-22 | 2018-04-13 | 2018-06-07 |  |  | No | Not Required | Not Required | Not Required
20INR0054 | Taygete Solar | SS Completed, FIS Started, IA | 7x Energy | 60393 Pig Creek 138kV | Pecos | WEST | 2020-12-01 | SOL | PV | 250 |  | 2018-02-26 | 2018-05-04 | 2018-02-26 |  | 2018-10-26 | Yes | Not Required | Not Required | Not Required
20INR0055 | Vaquero 2 Wind | SS Completed, FIS Started, No IA | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Zapata | SOUTH | 2020-12-31 | WIN | WT | 201.6 |  | 2018-03-15 | 2018-05-24 | 2018-03-15 |  |  | No | Not Required | Not Required | Not Required
20INR0056 | Point Mountain Solar | SS Completed, FIS Started, No IA | Hecate Energy | tap 345kV 11028 Odessa - 76000 N McCamey | Upton | WEST | 2020-06-01 | SOL | PV | 514 |  | 2018-04-02 | 2018-05-17 |  |  |  | No | Not Required | Not Required | Not Required
20INR0061 | Pflugerville 2 Solar | SS Completed, FIS Started, No IA | Core Solar | tap 138kV 7336 Gillie - 3650 Elgin | Travis | SOUTH | 2020-12-01 | SOL | PV | 120 |  | 2018-03-05 | 2018-04-19 |  |  |  | No | Not Required | Not Required | Not Required
20INR0064 | Black Angus | SS Completed, FIS Started, No IA | Apex Clean | tap 345kV 1730 WKrum - 6101 Riley | Webb | SOUTH | 2020-12-15 | WIN | WT | 352.8 |  | 2018-03-06 | 2018-05-03 | 2018-08-14 |  |  | No | Not Required | Not Required | Not Required
20INR0068 | Black Jack Creek Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 8164 Coleto - 8455 Lon Hill | Bee | SOUTH | 2020-12-31 | WIN | WT | 200.2 |  | 2018-04-02 | 2018-05-18 |  |  |  | No | Not Required | Not Required | Not Required
20INR0069 | Danish Fields Solar | SS Completed, FIS Started, No IA | Sunchase Power | 44200 Hillje 345kV or tap 345kV 44200 Hillje - 44040 Bailey | Wharton | SOUTH | 2021-02-01 | SOL | PV | 200 |  | 2018-04-12 | 2018-06-05 | 2018-08-21 |  |  | No | Not Required | Not Required | Not Required
20INR0070 | La Joya III | SS Completed, FIS Started, No IA | Terra-Gen | tap 138kV 8392 Bates - 8394 Liston | Hidalgo | SOUTH | 2019-12-31 | WIN | WT | 201.1 |  | 2018-04-12 | 2018-05-30 |  |  |  | No | Not Required | Not Required | Not Required
20INR0071 | La Joya IV | SS Completed, FIS Started, No IA | Terra-Gen | Goodwin (#8355) and La Grulla (#8798) buses | Hidalgo | SOUTH | 2019-12-31 | WIN | WT | 201.1 |  | 2018-04-12 | 2018-06-01 |  |  |  | No | Not Required | Not Required | Not Required
20INR0074 | Pitts Dudik Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 138kV 234 Chatt - 3515 Hubbard | Hill | NORTH | 2020-09-01 | SOL | PV | 90 |  | 2018-04-12 | 2018-05-18 | 2018-05-25 |  |  | No | Not Required | Not Required | Not Required
20INR0075 | Howle Solar | SS Completed, FIS Started, No IA | Belltown Power | 1908 Venus 138kV or tap 345kV 1906 Venus - 68090 Sam | Ellis | NORTH | 2020-08-01 | SOL | PV | 75 |  | 2018-05-15 | 2018-07-02 | 2018-08-14 |  |  | No | Not Required | Not Required | Not Required
20INR0080 | Frye Solar | SS Completed, FIS Started, No IA | Hecate Energy | tap 345kV 79501 Ogallala - 79503 Tule Canyon | Swisher | PANHANDLE | 2020-06-01 | SOL | PV | 500 |  | 2018-05-17 | 2018-07-02 |  |  |  | No | Not Required | Not Required | Not Required
20INR0081 | Strategic Energy | SS Completed, FIS Started, No IA | Alpin Sun | Tap 345kV 2435 Watermill - 68091 Navarro | Ellis | NORTH | 2020-11-01 | SOL | PV | 135 |  | 2018-04-26 | 2018-06-05 | 2018-07-18 |  |  | No | Not Required | Not Required | Not Required
20INR0082 | Vision Solar | SS Completed, FIS Started, No IA | Alpin Sun | tap 345kV 2428 Watermill - 68091 Navarro | Navarro | NORTH | 2020-11-01 | SOL | PV | 127.2 |  | 2018-04-26 | 2018-06-05 | 2018-05-17 |  |  | No | Not Required | Not Required | Not Required
20INR0083 | Baird North Wind | SS Completed, FIS Started, No IA | Chermac | tap 345kV 68005 WShack - 68050 Romney | Callahan | WEST | 2020-12-15 | WIN | WT | 300.3 |  | 2018-05-04 | 2018-06-12 | 2018-08-20 |  |  | No | Not Required | Not Required | Not Required
20INR0086 | Arroyo Solar | SS Completed, FIS Started, No IA | Belltown Power | tap Rio Hondo to La Palma 138-kV or 345-kV | Cameron | COASTAL | 2020-09-01 | SOL | PV | 150 |  | 2018-05-09 | 2018-07-09 |  |  |  | No | Not Required | Not Required | Not Required
20INR0088 | West Raymond Wind | SS Completed, FIS Started, No IA | Eon | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2020-09-15 | WIN | WT | 239.8 | MW Size | 2018-05-14 | 2018-07-09 | 2018-07-06 |  |  | No | Not Required | Not Required | Not Required
20INR0089 | Chisholm Grid Battery Storage | SS Completed, FIS Started, No IA | Able Grid Energy | 2082 Hicks 138kV | Tarrant | NORTH | 2020-03-01 | OTH | BA | 200 |  | 2018-05-14 | 2018-06-19 | 2018-05-14 |  |  | No | Not Required | Not Required | Not Required
20INR0091 | Misae Solar II | SS Completed, FIS Started, No IA | Misae Solar Park II | 60501 Tesla 345kV | Childress | PANHANDLE | 2020-07-01 | SOL | PV | 503.6 |  | 2018-05-15 | 2018-07-06 | 2018-05-15 |  |  | No | Not Required | Not Required | Not Required
20INR0098 | Danciger Solar | SS Completed, FIS Started, No IA | Tradewind Energy | tap 138kV 43120 Pledger - 43380 W Columbia | Brazoria | COASTAL | 2021-12-31 | SOL | PV | 200 |  | 2018-06-06 | 2018-08-01 |  |  |  | No | Not Required | Not Required | Not Required
20INR0100 | Westoria Storage | SS Completed, FIS Started, No IA | Tradewind Energy | Nash (Bus #42980) to West Columbia (Bus #43380) | Brazoria | COASTAL | 2021-12-31 | OTH | BA | 58 |  | 2018-06-07 | 2018-08-01 |  |  |  | No | Not Required | Not Required | Not Required
20INR0101 | Westoria Solar | SS Completed, FIS Started, No IA | Tradewind Energy | tap 138kV 42980 Nash - 43380 W Columbia | Brazoria | COASTAL | 2021-12-31 | SOL | PV | 200 |  | 2018-06-07 | 2018-07-30 |  |  |  | No | Not Required | Not Required | Not Required
20INR0102 | Atascosa I Solar | SS Completed, FIS Started, No IA | Core Solar | tap 138kV 8221 Big Foot - 8203 Pleasant | Atascosa | SOUTH | 2020-12-31 | SOL | PV | 126.6 |  | 2018-06-07 | 2018-08-24 |  |  |  | No | Not Required | Not Required | Not Required
20INR0104 | GoodAlta | SS Completed, FIS Started, No IA | Alta Power | 3483 Goodloe 138kV | Navarro | NORTH | 2021-04-01 | GAS | GT | 150 | COD | 2018-07-26 | 2018-09-18 |  |  |  | No | Not Required | Not Required
20INR0106 | Wang Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 138kV 3410 LakeCr1 - 3420 TempPEC or tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2020-10-01 | SOL | PV | 120 |  | 2018-06-14 | 2018-08-13 | 2018-08-29 |  |  | No | Not Required | Not Required | Not Required
20INR0111 | Dusky Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 3522 Hillsboro -3546 Lake Whitney | Hill | NORTH | 2020-12-30 | SOL | PV | 165 |  | 2018-06-29 | 2018-09-11 | 2018-06-29 |  |  | No | Not Required | Not Required | Not Required
20INR0112 | Walstrom | SS Completed, FIS Started, No IA | Castleman Power | 46220 Peters 138kV | Austin | SOUTH | 2020-05-01 | GAS | GT | 200 |  | 2018-07-03 | 2018-09-18 |  |  |  | No | Not Required | Not Required
20INR0118 | Merrifield Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 69kV 3523 Hillsboro - 3543 Mertens or tap 345kV 1906 Venus - 68090 Sam | Hill | NORTH | 2020-12-01 | SOL | PV | 80 |  | 2018-06-29 | 2018-09-18 |  |  |  | No | Not Required | Not Required | Not Required
20INR0119 | Azure Sky Wind 1 | SS Completed, FIS Started, No IA | Tradewind Energy | 60515 Clear Crossing 345kV or tap 60515 - 1421 WillowCr | Throckmorton | WEST | 2020-09-30 | WIN | WT | 350 |  | 2018-06-29 | 2018-08-27 |  |  |  | No | Not Required | Not Required | Not Required
20INR0126 | Robles Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 8283 Asherton 138kV | Dimmit | SOUTH | 2020-12-31 | SOL | PV | 200 |  | 2018-07-18 | 2018-10-04 | 2018-07-18 |  |  | No | Not Required | Not Required | Not Required
20INR0128 | EK Tipton Solar | SS Completed, FIS Started, No IA | Energie Kontor | 6673 Musquiz 138kV | Reeves | WEST | 2020-12-31 | SOL | PV | 101.63 |  | 2018-09-27 | 2018-11-19 |  |  |  | No | Not Required | Not Required | Not Required
20INR0129 | Foxtrot Wind | SS Completed, FIS Started, No IA | Lincoln Clean | Pawnee 345 kV bus 5725 | Karnes | SOUTH | 2020-12-01 | WIN | WT | 504 |  | 2018-07-26 | 2018-09-14 | 2018-07-26 |  |  | No | Not Required | Not Required | Not Required
20INR0130 | Ramsey Solar | SS Completed, FIS Started, No IA | Hecate Energy | 44200 Hillje OR tap 345kV 9073 Holman - 44200 Hillje | Wharton | SOUTH | 2020-06-01 | SOL | PV | 514 |  | 2018-10-10 | 2018-11-21 |  |  |  | No | Not Required | Not Required | Not Required
20INR0132 | Altajac | SS Completed, FIS Started, No IA | Alta Power | 3253 Jaxvlsw 138kV | Cherokee | NORTH | 2021-04-01 | GAS | GT | 150 | COD | 2018-07-18 | 2018-09-07 |  |  |  | No | Not Required | Not Required
20INR0134 | Half Moon Solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2020-12-31 | SOL | PV | 151.2 |  | 2018-09-13 | 2018-11-09 |  |  |  | No | Not Required | Not Required | Not Required
20INR0135 | Half Moon Battery | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Hidalgo | SOUTH | 2020-12-31 | OTH | BA | 30.2 |  | 2018-09-13 | 2018-11-09 |  |  |  | No | Not Required | Not Required | Not Required
20INR0142 | Ajax Wind | SS Completed, FIS Started, No IA | Lincoln Clean | 345kV line RILEY 6101 - Bowman 1422 | Wilbarger | WEST | 2021-12-01 | WIN | WT | 630 |  | 2018-08-14 | 2018-10-19 | 2018-08-14 |  |  | No | Not Required | Not Required | Not Required
20INR0143 | Soda Lake Solar 2 | SS Completed, FIS Started, IA | Arrington Solar | Tap 138kV 6601 Rio Pecos - 60014 Spudder | Crane | WEST | 2020-12-31 | SOL | PV | 200 |  |  | 2016-11-08 |  |  | 2018-08-20 | No | Not Required | Not Required | Not Required
20INR0144 | Longbow Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 42870 Liverpool 138kV | Brazoria | COASTAL | 2020-03-01 | OTH | BA | 35 |  | 2017-08-16 | 2017-10-13 | 2017-08-16 |  |  | No | Not Required | Not Required | Not Required
20INR0146 | Angus Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 177 Bosque - 181 Cayote | Bosque | NORTH | 2020-08-31 | OTH | BA | 63 |  | 2017-11-13 | 2018-01-02 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
20INR0147 | Stillwater Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 345kV 8905 N Edinb - 8455 Lon Hill | Nueces | COASTAL | 2020-08-31 | OTH | BA | 72 |  | 2017-11-13 | 2018-01-15 | 2017-11-13 |  |  | No | Not Required | Not Required | Not Required
20INR0149 | Dusky Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 3522 Hillsboro -3546 Lake Whitney | Hill | NORTH | 2020-12-30 | OTH | BA | 83 |  | 2018-06-29 | 2018-09-11 | 2018-06-29 |  |  | No | Not Required | Not Required | Not Required
20INR0150 | Robles Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 8283 Asherton 138kV | Dimmit | SOUTH | 2020-12-31 | OTH | BA | 100 |  | 2018-07-18 | 2018-10-04 | 2018-07-18 |  |  | No | Not Required | Not Required | Not Required
20INR0151 | Prairie Point Wind | SS Completed, FIS Started, No IA | Nextera | 1752 Whitemound 138 kV | Grayson | NORTH | 2021-12-01 | WIN | WT | 200 |  | 2018-08-17 | 2018-10-03 | 2018-08-17 |  |  | No | Not Required | Not Required | Not Required
20INR0152 | Prairie Point Battery | SS Completed, FIS Started, No IA | Nextera | 1752 Whitemound 138 kV | Grayson | NORTH | 2021-12-01 | OTH | BA | 41 |  | 2018-08-17 | 2018-10-03 | 2018-08-17 |  |  | No | Not Required | Not Required | Not Required
20INR0153 | Tiger Wind | SS Completed, FIS Started, No IA | Nextera | (68000) West Shackelford | Nolan | WEST | 2020-12-01 | WIN | WT | 300 |  | 2018-10-10 | 2018-11-16 |  |  |  | No | Not Required | Not Required | Not Required
20INR0154 | Fort McKavett Wind | SS Completed, FIS Started, No IA | Nextera | loop on 60618 Edison - 7046 Kendal 345kV | Menard | WEST | 2020-12-01 | WIN | WT | 300 |  | 2018-08-17 | 2018-10-03 | 2018-08-17 |  |  | No | Not Required | Not Required | Not Required
20INR0156 | Thunder Creek | SS Completed, FIS Started, No IA | Nextera | 1430 Graham 345kV | Hardeman | WEST | 2021-12-01 | WIN | WT | 200 |  | 2018-08-17 | 2018-10-05 | 2018-08-17 |  |  | No | Not Required | Not Required | Not Required
20INR0160 | R-Cube Wind | SS Completed, FIS Started, No IA | Nextera | 1730 Krum 345kV | Denton | NORTH | 2020-12-31 | WIN | WT | 1000 |  | 2018-08-21 | 2018-11-08 | 2018-08-21 |  |  | No | Not Required | Not Required | Not Required
20INR0162 | Diamondback Solar | SS Completed, FIS Started, No IA | Nextera | 80355 Del Sol 345kV | Starr | SOUTH | 2020-12-31 | SOL | PV | 201.6 |  | 2018-09-13 | 2018-12-06 |  |  |  | No | Not Required | Not Required | Not Required
20INR0163 | Sand Bluff Repower | SS Completed, FIS Started, No IA | Eon | 1333 McDonald 138kV | Glasscock | WEST | 2020-06-30 | WIN | WT | 7.4 |  | 2018-08-28 | 2018-09-05 | 2018-08-28 |  |  | No | Not Required | Not Required | Not Required
20INR0164 | Neeley Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV 1907 Venus - 68090 Sam | Hill | NORTH | 2020-12-01 | SOL | PV | 175 |  | 2018-08-29 | 2018-11-08 |  |  |  | No | Not Required | Not Required | Not Required
20INR0202 | Owens Solar | SS Completed, FIS Started, No IA | Belltown Power | tap 345kV Shackelford (#68000) to Navarro (#68091) | Bosque | NORTH | 2020-10-15 | SOL | PV | 200 | COD | 2018-09-19 | 2018-10-03 |  |  |  | No | Not Required | Not Required | Not Required
20INR0204 | Blue Bell Solar II | SS Completed, FIS Started, No IA | CAP RIDGE WIND IV LLC | 76090 Divide 345kV | Sterling | WEST | 2020-07-31 | SOL | PV | 101.25 |  | 2018-10-23 | 2018-12-13 | 2018-10-03 |  |  | No | Not Required | Not Required | Not Required
20INR0206 | PES1 | SS Completed, FIS Started, No IA | ProEnergy Services LLC | 47150 H O Clarke 138kV | Harrison | EAST-SPP | 2020-06-01 | GAS | GT | 484 |  | 2018-10-23 | 2018-11-16 | 2018-10-11 |  |  | No | Not Required | Not Required
20INR0214 | Noble Solar | SS Completed, FIS Started, No IA | Belltown Power Texas, LLC | 1730 Krum 345kV | Denton | NORTH | 2020-12-01 | SOL | PV | 300 |  | 2018-11-06 | 2018-12-17 |  |  |  | No | Not Required | Not Required | Not Required
20INR0216 | Starr Solar Ranch | SS Completed, FIS Started, No IA | Starr Solar Ranch LLC | 8795 Roma 138kV | Starr | SOUTH | 2020-10-01 | SOL | PV | 135.99 |  | 2018-11-07 | 2018-12-14 | 2018-11-07 |  |  | No | Not Required | Not Required | Not Required
20INR0219 | Eunice Solar | SS Started, FIS Started, No IA | 2W Permian Solar LLC | tap 345kV 79650 Clearfork - 79630 Telephone Rd | Andrews | WEST | 2020-12-31 | SOL | PV | 403.8 | FIS Request | 2018-12-06 |  | 2018-11-30 |  |  | No |  |  | Not Required
20INR0220 | Eunice Storage | SS Started, FIS Started, No IA | 2W Permian Solar LLC | tap 345kV 79650 Clearfork - 79630 Telephone Rd | Andrews | WEST | 2020-12-31 | OTH | BA | 40.26 | FIS Request | 2018-12-06 |  | 2018-11-30 |  |  | No |  |  | Not Required
20INR0221 | Braes Power Plant | SS Started, FIS Started, No IA | ProEnergy Services LLC | 44650 Smithers 345kV | Fort Bend | HOUSTON | 2020-08-01 | GAS | GT | 484 | FIS Request | 2018-12-06 |  | 2018-12-01 |  |  | No
20INR0224 | Ponta Power Plant | SS Started, FIS Started, No IA | Pro Energy Services LLC | 3109 Stryker Creek 345kV | Cherokee | NORTH | 2020-06-01 | GAS | GT | 484 | FIS Request | 2018-12-18 |  | 2018-12-07 |  |  | No
20INR0230 | Markum Solar | SS Started, FIS Started, No IA | L Bar L Ranch LP | 177 Bosque 138kV | McLennan | NORTH | 2021-05-01 | SOL | PV | 134.89 | FIS Request MW Size COD | 2018-12-18 |  | 2018-12-18 |  |  | No |  |  | Not Required
21INR0007 | Deepwater | SS Completed, FIS Started, No IA | AES | 40450 Deepwater 345kV | Harris | HOUSTON | 2021-04-30 | GAS | GT | 462.2 |  | 2017-12-05 | 2018-02-01 | 2017-12-05 |  |  | No
21INR0008 | Samson Solar | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2021-12-31 | SOL | PV | 200 |  | 2018-04-12 | 2018-06-12 |  |  |  | No | Not Required | Not Required | Not Required
21INR0009 | Callisto | SS Completed, FIS Started, No IA | Intersect Power | 59900 Long Draw 345kV | Borden | WEST | 2021-12-31 | SOL | PV | 300 |  | 2018-04-12 | 2018-06-13 | 2018-08-14 |  |  | No | Not Required | Not Required | Not Required
21INR0015 | Arroyo Del Bisonte Solar | SS Completed, FIS Started, No IA | Sunchase Power | tap 345kV 44005 WAP - 44040 Bailey or 44000 WAP - 44200 Hillje | Fort Bend | HOUSTON | 2021-04-01 | SOL | PV | 300 |  | 2018-05-09 | 2018-07-06 | 2018-08-21 |  |  | No | Not Required | Not Required | Not Required
21INR0016 | Danish Fields II | SS Completed, FIS Started, No IA | Sunchase Power | 44200 Hillje 345kV or tap 345kV 5915 STP - 44000 WAP | Matagorda | COASTAL | 2021-04-30 | SOL | PV | 200 |  | 2018-05-10 | 2018-07-11 | 2018-08-21 |  |  | No | Not Required | Not Required | Not Required
21INR0017 | Danish Fields III | SS Completed, FIS Started, No IA | Sunchase Power | 44200 Hillje 345kV or tap 345kV 5915 STP - 44000 WAP | Matagorda | COASTAL | 2021-06-30 | SOL | PV | 200 |  | 2018-05-10 | 2018-07-11 | 2018-08-27 |  |  | No | Not Required | Not Required | Not Required
21INR0019 | Zier Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 8252 Brackett - 78255 PintCr | Kinney | SOUTH | 2021-05-31 | SOL | PV | 120 |  | 2018-05-24 | 2018-07-20 | 2018-05-24 |  |  | No | Not Required | Not Required | Not Required
21INR0020 | El Zorro Solar | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 80439 La Quinta - 8297 Bruni 138kV | Webb | SOUTH | 2021-02-01 | SOL | PV | 253.3 |  | 2018-06-29 | 2018-09-13 | 2018-06-29 |  |  | No | Not Required | Not Required | Not Required
21INR0021 | Green Holly Solar | SS Completed, FIS Started, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-08-01 | SOL | PV | 413.6 |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | No | Not Required | Not Required | Not Required
21INR0022 | Red Holly Solar | SS Completed, FIS Started, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-07-01 | SOL | PV | 260 |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | No | Not Required | Not Required | Not Required
21INR0024 | Samson Solar 2 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2021-12-31 | SOL | PV | 200 | FIS Request |  | 2018-06-12 |  |  |  | No | Not Required | Not Required | Not Required
21INR0026 | Juno Solar | SS Completed, FIS Started, No IA | Intersect Power | 59900 Longdraw 345kV | Borden | WEST | 2021-05-15 | SOL | PV | 495 |  | 2018-08-14 | 2018-10-25 |  |  |  | No | Not Required | Not Required | Not Required
21INR0027 | Zier Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | tap 138kV 8252 Brackett - 78255 PintCr | Kinney | SOUTH | 2021-05-31 | OTH | BA | 60 |  | 2018-05-24 | 2018-07-20 | 2018-05-24 |  |  | No | Not Required | Not Required | Not Required
21INR0028 | El Zorro Storage | SS Completed, FIS Started, No IA | Cypress Creek Renewables | 80439 La Quinta - 8297 Bruni 138kV | Webb | SOUTH | 2021-02-01 | OTH | BA | 126.65 |  | 2018-06-29 | 2018-09-13 | 2018-06-29 |  |  | No | Not Required | Not Required | Not Required
21INR0029 | Green Holly Storage | SS Completed, FIS Started, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-08-01 | OTH | BA | 50 |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | No | Not Required | Not Required | Not Required
21INR0032 | Juno Storage | SS Completed, FIS Started, No IA | Intersect Power | 59900 Long Draw 345kV | Borden | WEST | 2021-05-15 | OTH | BA | 495 |  | 2018-08-14 | 2018-10-25 |  |  |  | No | Not Required | Not Required | Not Required
21INR0033 | Red Holly Storage | SS Completed, FIS Started, No IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2021-07-01 | OTH | BA | 50 | FIS Request | 2018-09-27 | 2018-12-18 |  |  |  | No | Not Required | Not Required | Not Required
21INR0201 | Brandon | SS Completed, FIS Started, No IA | Lubbock Power and Light | Brandon 69 kV | Lubbock | PANHANDLE | 2021-06-01 | GAS | GT | 21.5 |  | 2018-09-12 | 2018-09-12 | 2018-09-12 |  |  | No | Not Required | Not Required
21INR0202 | R Massengale | SS Completed, FIS Started, No IA | Lubbock Power and Light | MacKenzie 60 kV | Lubbock | PANHANDLE | 2021-06-01 | GAS | GT | 60 |  | 2018-09-12 | 2018-09-12 | 2018-09-12 |  |  | No | Not Required | Not Required
21INR0204 | Lumina | SS Completed, FIS Started, No IA | IP Lumina, LLC | 11305 Dermott 345kV | Scurry | WEST | 2021-12-31 | SOL | PV | 313.2 |  | 2018-09-27 | 2018-11-08 |  |  |  | No | Not Required | Not Required | Not Required
21INR0205 | Radian | SS Completed, FIS Started, No IA | IP Radian, LLC | 1444 Brown 345kV | Brown | NORTH | 2021-12-31 | SOL | PV | 313.2 |  | 2018-09-27 | 2018-11-08 |  |  |  | No | Not Required | Not Required | Not Required
21INR0206 | Elrond | SS Completed, FIS Started, No IA | IP Elrond, LLC | 6161 Paint Creek 138kV | Haskell | WEST | 2021-12-31 | SOL | PV | 313.2 |  | 2018-09-27 | 2018-11-14 |  |  |  | No | Not Required | Not Required | Not Required
21INR0207 | Quantum | SS Completed, FIS Started, No IA | IP Quantum, LLC | 60515 Clear Crossing 345kV | Haskell | WEST | 2021-12-31 | SOL | PV | 313.2 |  | 2018-09-27 | 2018-11-14 |  |  |  | No | Not Required | Not Required | Not Required
21INR0213 | Vancourt | SS Completed, FIS Started, No IA | Rayos del Sol II Solar Project, LLC | tap 138kV 80103 Rangerville - 8554 Mesquite | Cameron | COASTAL | 2021-12-31 | SOL | PV | 50 |  | 2018-11-07 | 2018-12-12 |  |  |  | No | Not Required | Not Required | Not Required
21INR0232 | Cowboy Solar | SS Started, FIS Started, No IA | AP Solar Holdings LLC | tap 138kV 5827 Moore - 5885 Downie | Frio | SOUTH | 2021-01-01 | SOL | PV | 152.49 | Proj Name MW Size FIS Request | 2018-12-07 |  | 2018-12-07 |  |  | No |  |  | Not Required
21INR0233 | Taygete II Solar | SS Started, FIS Started, No IA | TAYGETE ENERGY PROJECT LLC | 60393 Pig Creek 138kV | Pecos | WEST | 2021-02-01 | SOL | PV | 256.25 | FIS Request COD | 2018-12-17 |  | 2018-12-13 |  |  | No |  |  | Not Required
21INR0244 | Madero Grid | SS Started, FIS Started, No IA | Madero Grid | 138 kV Railroad station (Bus #8824) | Hidalgo | SOUTH | 2021-05-31 | OTH | BA | 201.96 | FIS Request | 2018-12-20 |  | 2018-12-19 |  |  | No |  |  | Not Required
22INR0001 | Samson Solar 3 | SS Completed, FIS Started, No IA | Invenergy | tap 345kV 1692 Paris - 1695 Monticello | Lamar | NORTH | 2022-12-31 | SOL | PV | 200 | FIS Request |  | 2018-06-12 |  |  |  | No | Not Required | Not Required | Not Required

## GINR Trends
GINR Trends
Reflects all projects for which a Security Screening Study has been requested.
Nameplate capacity will change across time due to additional projects, cancelations, expirations, adjustments from study results, and projects being placed into service.
| Year | Month | Total Active Projects | Project Count | [5 empty] | Project Capacity (MW)
|  |  |  | GINR milestones | [5 empty] | Fuel Type
|  |  |  | Initial Screening Study | Screening Study Complete | In Full Study | Completed Full Study | Signed Interconnection Agreement | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Other
| 2015 | Dec | 255 | 3 | 21 | 131 | 10 | 90 | 15 | 24095 | 8509 | 27686 | 0 | 240 | 0 | 614
| 2016 | Jan | 241 | 4 | 13 | 124 | 10 | 90 | 14 | 24472 | 7713 | 24383 | 0 | 240 | 0 | 614
| 2016 | Feb | 236 | 3 | 12 | 118 | 14 | 89 | 8 | 23508 | 7757 | 23058 | 0 | 240 | 0 | 644
| 2016 | Mar | 236 | 3 | 16 | 112 | 12 | 93 | 5 | 24197 | 7482 | 23158 | 0 | 240 | 0 | 644
| 2016 | Apr | 241 | 8 | 12 | 111 | 11 | 99 | 5 | 24951 | 7762 | 22982 | 0 | 240 | 0 | 644
| 2016 | May | 236 | 4 | 16 | 108 | 8 | 100 | 9 | 25304 | 7414 | 23149 | 0 | 240 | 0 | 644
| 2016 | Jun | 232 | 12 | 14 | 104 | 8 | 94 | 8 | 25215 | 8321 | 22471 | 0 | 240 | 0 | 644
| 2016 | Jul | 231 | 13 | 16 | 98 | 7 | 96 | 7 | 25215 | 8321 | 22304 | 0 | 240 | 0 | 644
| 2016 | Aug | 235 | 17 | 24 | 88 | 6 | 100 | 5 | 25895 | 9538 | 21077 | 0 | 240 | 0 | 694
| 2016 | Sep | 226 | 10 | 22 | 90 | 6 | 98 | 7 | 25254 | 9391 | 19671 | 0 | 240 | 0 | 694
| 2016 | Oct | 250 | 16 | 27 | 93 | 6 | 99 | 2 | 26643 | 12439 | 19771 | 0 | 240 | 0 | 674
| 2016 | Nov | 247 | 18 | 31 | 98 | 3 | 98 | 3 | 26643 | 12439 | 19771 | 0 | 240 | 0 | 674
| 2016 | Dec | 254 | 23 | 33 | 103 | 2 | 96 | 4 | 26732 | 13724 | 18816 | 0 | 240 | 0 | 624
| 2017 | Jan | 257 | 16 | 36 | 105 | 4 | 96 | 2 | 26270 | 14498 | 18816 | 0 | 240 | 0 | 624
| 2017 | Feb | 263 | 8 | 33 | 127 | 2 | 93 | 5 | 26512 | 14958 | 19016 | 0 | 240 | 0 | 30
| 2017 | Mar | 264 | 11 | 27 | 131 | 3 | 92 | 3 | 26593 | 15338 | 16750 | 0 | 240 | 0 | 0
| 2017 | Apr | 284 | 28 | 28 | 136 | 3 | 89 | 5 | 28470 | 17054 | 19316 | 0 | 240 | 0 | 0
| 2017 | May | 287 | 23 | 35 | 139 | 3 | 87 | 4 | 28259 | 18012 | 17620 | 0 | 240 | 0 | 0
| 2017 | Jun | 320 | 33 | 45 | 154 | 3 | 85 | 4 | 31835 | 22275 | 15656 | 0 | 240 | 0 | 30
| 2017 | Jul | 323 | 38 | 44 | 155 | 3 | 83 | 7 | 30279 | 21974 | 15656 | 0 | 0 | 0 | 30
| 2017 | Aug | 333 | 32 | 61 | 155 | 5 | 80 | 11 | 30068 | 23814 | 14357 | 0 | 0 | 0 | 0
| 2017 | Sep | 336 | 35 | 60 | 157 | 5 | 79 | 18 | 29915 | 24089 | 12001 | 0 | 0 | 0 | 0
| 2017 | Oct | 339 | 25 | 66 | 163 | 9 | 76 | 6 | 30090 | 24729 | 14201 | 0 | 0 | 0 | 0
| 2017 | Nov | 340 | 14 | 64 | 172 | 15 | 75 | 17 | 29882 | 24893 | 13747 | 0 | 0 | 0 | 0
| 2017 | Dec | 337 | 7 | 57 | 166 | 19 | 73 | 8 | 30198 | 24123 | 13969 | 0 | 0 | 0 | 30
| 2018 | Jan | 335 | 15 | 56 | 169 | 21 | 74 | 17 | 31420 | 22739 | 12768 | 0 | 0 | 0 | 0
| 2018 | Feb | 334 | 11 | 46 | 177 | 27 | 73 | 9 | 32258 | 22413 | 12727 | 0 | 0 | 0 | 0
| 2018 | Mar | 340 | 14 | 41 | 179 | 27 | 79 | 8 | 32897 | 23515 | 12065 | 0 | 0 | 0 | 0
| 2018 | Apr | 349 | 18 | 48 | 172 | 30 | 81 | 4 | 33427 | 24709 | 13484 | 0 | 0 | 0 | 0
| 2018 | May | 369 | 33 | 36 | 180 | 34 | 86 | 13 | 33799 | 27766 | 13442 | 0 | 0 | 0 | 200
| 2018 | Jun | 379 | 32 | 42 | 190 | 27 | 88 | 6 | 34376 | 28448 | 13674 | 0 | 0 | 0 | 522
| 2018 | Jul | 404 | 34 | 60 | 197 | 25 | 88 | 6 | 37708 | 30518 | 11668 | 0 | 0 | 0 | 522
| 2018 | Aug | 417 | 26 | 57 | 220 | 26 | 88 | 11 | 40851 | 29649 | 10814 | 0 | 0 | 0 | 2177
| 2018 | Sep | 426 | 30 | 67 | 212 | 26 | 91 | 15 | 40327.45 | 31655.3 | 8589.6 | 0 | 0 | 0 | 1889
| 2018 | Oct | 429 | 26 | 60 | 221 | 24 | 98 | 4 | 40237.59 | 32248.91 | 9073.6 | 0 | 0 | 0 | 1889
| 2018 | Nov | 443 | 23 | 59 | 235 | 26 | 100 | 7 | 40283.09 | 36682.4 | 7503.4 | 0 | 0 | 0 | 2048.35
| 2018 | Dec | 465 | 31 | 67 | 237 | 27 | 103 | 9 | 39596.45 | 40732.49 | 9249.4 | 0 | 0 | 0 | 2342.82
Note: Other contains all Fuel and Technology Types not in the Solar, Wind, Gas or Battery categories.
Forecast Zones for the Capacity, Demand & Reserves (CDR) Report

## data_GINR Trends_1 (hidden)
| # Initial Screening study | # Screening Study Complete | # in Full Study | # Completed Full Study | # Signed Interconnect Agreement | MW Capacity
Dec-17 | 7 | 57 | 166 | 19 | 73 | 68320
Jan-18 | 15 | 56 | 169 | 21 | 74 | 66927
Feb-18 | 11 | 46 | 177 | 27 | 73 | 67398
Mar-18 | 14 | 41 | 179 | 27 | 79 | 68477
Apr-18 | 18 | 48 | 172 | 30 | 81 | 71620
May-18 | 33 | 36 | 180 | 34 | 86 | 75207
Jun-18 | 32 | 42 | 190 | 27 | 88 | 77020
Jul-18 | 34 | 60 | 197 | 25 | 88 | 80416
Aug-18 | 26 | 57 | 220 | 26 | 88 | 83491
Sep-18 | 30 | 67 | 212 | 26 | 91 | 82461.35
Oct-18 | 26 | 60 | 221 | 24 | 98 | 83449.1
Nov-18 | 23 | 59 | 235 | 26 | 100 | 86517.24
Dec-18 | 31 | 67 | 237 | 27 | 103 | 91921.16

## data_GINR Trends_2 (hidden)
| MW Natural Gas | Nuclear | Coal | Wind | Solar | Biomass | Other | Total Project Count | Cancelled Project Count
Dec-17 | 13969 | 0 | 0 | 30198 | 24123 | 0 | 30 | 337 | 8
Jan-18 | 12768 | 0 | 0 | 31420 | 22739 | 0 | 0 | 335 | 17
Feb-18 | 12727 | 0 | 0 | 32258 | 22413 | 0 | 0 | 334 | 9
Mar-18 | 12065 | 0 | 0 | 32897 | 23515 | 0 | 0 | 340 | 8
Apr-18 | 13484 | 0 | 0 | 33427 | 24709 | 0 | 0 | 349 | 4
May-18 | 13442 | 0 | 0 | 33799 | 27766 | 0 | 200 | 369 | 13
Jun-18 | 13674 | 0 | 0 | 34376 | 28448 | 0 | 522 | 379 | 6
Jul-18 | 11668 | 0 | 0 | 37708 | 30518 | 0 | 522 | 404 | 6
Aug-18 | 10814 | 0 | 0 | 40851 | 29649 | 0 | 2177 | 417 | 11
Sep-18 | 8589.6 | 0 | 0 | 40327.45 | 31655.3 | 0 | 1889 | 426 | 15
Oct-18 | 9073.6 | 0 | 0 | 40237.59 | 32248.91 | 0 | 1889 | 429 | 4
Nov-18 | 7503.4 | 0 | 0 | 40283.09 | 36682.4 | 0 | 2048.35 | 443 | 7
Dec-18 | 9249.4 | 0 | 0 | 39596.45 | 40732.49 | 0 | 2342.82 | 465 | 9

## data_GINR Trends_3 (hidden)
|  | Gas | Wind | Solar | Battery | Other
COASTAL | 2018 |  | 162.9
| 2019 | 664 | 2041.7
| 2020 | 400 | 1769 | 1663.9 | 233.35
| 2021 |  |  | 1050 | 156.8
HOUSTON | 2018 | 12
| 2019 | 11
| 2020 | 1202.6 |  | 540
| 2021 | 552.2 |  | 300
WEST | 2018 |  | 277.4
| 2019 |  | 6462.34 | 3107.3
| 2020 |  | 7534.9 | 9969.64 | 81.26
| 2021 | 742.9 | 2397.5 | 6743.75 | 886.6
| 2022 | 742.9 |  | 600
NORTH | 2019 | 44 | 592.8 | 373
| 2020 | 1134 | 2154.2 | 4419.6 | 346
| 2021 | 1957.5 | 700.2 | 2349.69 | 82
| 2022 | 328 |  | 1050
PANHANDLE | 2019 |  | 2040.7 | 340.8
| 2020 |  | 3917.5 | 1604.6
| 2021 | 81.5 | 653.9 | 150
SOUTH | 2019 | 145 | 3847.8 | 825 | 38
| 2020 | 350 | 4143.61 | 2610.39 | 130.2
| 2021 | 397.8 | 900 | 3034.82 | 388.61